## Current-schedule
Pharm Ops - Non-Sterile | [56 empty] | 1Q Sched Metrics |  | PE Utilization | 4.5385 | Room Utiliz | 70.94% | Equip Utilization | 65.09% | [5 empty] | 2Q Sched Metrics |  | PE Utilization | 3.8462 | Room Utiliz | 71.31% | Equip Utilization | 87.57% | [5 empty] | 3Q Sched Metrics |  | PE Utilization | 7.9 | Room Utiliz | 78% | Equip Utilization | 83.08% | [5 empty] | 4Q Sched Metrics |  | PE Utilization | 6.9231 | Room Utiliz | 72.31% | Equip Utilization | 97.04% | [5 empty] | 1Q Sched Metrics |  | PE Utilization | 0 | Room Utiliz | 71.54% | Equip Utilization | 76.22% | [5 empty] | 2Q Sched Metrics |  | PE Utilization | #DIV/0! | Room Utiliz | 5% | Equip Utilization | #DIV/0! | [5 empty] | 3Q Sched Metrics |  | PE Utilization | #DIV/0! | Room Utiliz | #DIV/0! | Equip Utilization | #DIV/0! | [5 empty] | 4Q Sched Metrics |  | PE Utilization | #DIV/0! | Room Utiliz | #DIV/0! | Equip Utilization | #DIV/0!
880 OSD Schedule | 1Q2023 | [12 empty] | 2Q2023 | [12 empty] | 3Q2023 | [12 empty] | 4Q2023 | [13 empty] | 1Q2024 | [12 empty] | 2Q2024 | [12 empty] | 3Q2024 | [12 empty] | 4Q2024 | [12 empty] | 1Q2025 | [12 empty] | 2Q2025 | [12 empty] | 3Q2025 | [12 empty] | 4Q2025
Development Batches in Green
GMP Batches in Blue (GCS FPU Pkg in BOLD)
Maintenance (link to plan) | [73 empty] | Mem day |  |  | Juneteenth |  | 2024-07-04 | [11 empty] | MTS
Train unavailable due to parallel work/room limitations | [75 empty] | Safety Audit | [7 empty] | Internal Audit | [5 empty] | Anna OOO | Anna OOO | Anna OOO |  | SporKlenz | AAPS |  |  |  | 4Q safety | Tsgiving |  |  |  | Shutdown | [18 empty] | PASX BLACKOUT
Week starting | time axis 2023-01-01 to 2026-01-26
ISO week | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5
Process | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 1 | 2 | 4 | 2 | 2 | 2 | 3 | 4 | 5 | 4 | 5 | 4 | 6 | 5 | 4 | 6 | 8 | 7 | 4 | 3 | 4 | 5 | 5 | 5 | 5 | 4 | 5 | 6 | 4 | 6 | 1 | Shutdown | Shutdown | Bring up | 6 | 4 | 3 | 5 | 3 | 3 | 2 | 5 | 3 | 4 | 4 | 3 | 3 | 4 | 5 | 6 | 3 | 3 | 5 | 1 | 1 | 0 | 2 | 3 | 5 | 5 | 3 | 4 | 3 | 4 | 3 | 6 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 3 | 1 | 3 | 2 | 3 | 3 | 3 | 2
Tablet Compression (A1) - XL100 | 2023-04-30: MK-1084 Setup; 2023-05-07: Batch 1; 2023-05-14: Cleaning; 2023-07-02: Holiday; 2023-07-09: Shutdown; 2023-07-16: Shutdown; 2023-07-23: Shutdown; 2023-07-30: Bringup; 2023-12-17: MK-1084 setup; 2023-12-24: Holiday; 2023-12-31: Shutdown; 2024-01-08: Bringup; 2024-01-22: MK-1084; 2024-01-29: MK-1084; 2024-02-05: MK-1084; 2024-02-12: MK-1084; 2024-02-19: Cleaning, swab;; 2024-02-26: Setup (IH-740 testing); 2024-03-04: MK-6552; 2024-03-11: Cleaning; 2024-03-18: MK-6552; 2024-03-25: Cleaning; 2024-04-01: Swab, micro challenge; 2024-04-15: Swab/PM; 2024-04-22: Training; 2024-04-29: Training; 2024-06-03: Setup (IH-740 testing); 2024-06-10: MK-6552; 2024-06-17: Cleaning; 2024-06-24: MK-6552; 2024-07-01: Cleaning; 2024-07-29: inc hold; 2024-08-05: waiting HEPA replacement; 2024-09-30: Setup; 2024-10-07: MK-8507 1 batch; 2024-10-21: Cleaning; 2024-10-28: VRL challenge release; 2024-11-18: MK-1084 Conv x 2; 2024-12-30: Blend, RC, XL100; 2025-01-06: Setup; 2025-01-13: MK-3543; 2025-01-20: Clean; 2025-01-27: Dev MK-8527; 2025-02-03: MK-8527 1 batch; 2025-02-10: Clean; 2025-02-17: MK-6916; 2025-02-24: MK-6916; 2025-03-03: MK-6916; 2025-03-10: Clean; 2025-03-17: VRL Challenge; 2025-04-28: XXXX Clinical Batch; 2025-06-02: MK-0616 FDC; 2025-06-09: MK-0616 FDC; 2025-06-23: MK-0616 FDC; 2025-06-30: MK-0616 FDC; 2025-09-22: MK-0616 PEDS
Tablet Compression (A2) - XM12 | 2024-03-04: Move XM12; 2024-03-11: Testing; 2024-03-18: Testing; 2024-03-25: Training - setup/disassembly; 2024-04-01: Downtime; 2024-04-08: IH740; 2024-04-15: PM/Setup; 2024-04-22: Training; 2024-04-29: CV PTM-300; 2024-05-06: CV PTM-300; 2024-05-13: XM12 training; 2024-05-20: XM12 training; 2024-05-27: XM 12 CV; 2024-06-03: XM 12 CV; 2024-06-10: Turnaround; 2024-06-17: Tablet production for film coater shakedown; 2024-07-08: XL100 CV in 119; 2024-07-22: MK-1084 Dev batch; 2024-09-02: Korsch training; 2024-09-16: MK-1084; 2024-09-23: F/E; 2024-09-30: MK-1084; 2024-10-14: PTM300 Introduction; 2024-11-04: XM12 to 1251 Storage; 2024-12-30: FC:; 2025-01-06: Setup; 2025-01-20: MK-3543; 2025-01-27: Clean; 2025-02-03: Dev MK-8527; 2025-02-10: MK-8527; 2025-02-17: Clean; 2025-03-24: available only if 1242 setup available and free from TSG; 2025-06-23: GLP1?; 2025-06-30: GLP 1? Including spray dryer; 2025-07-28: GLP1; 2025-08-04: GLP1; 2025-08-11: GLP1
Autoencapsulator (B) | 2023-02-05: MK-1942 Setup; 2023-02-12: Dev; 2023-02-19: Batch 1; 2023-02-26: Batch 2; 2023-03-05: Cleaning; 2023-06-11: MK-1167 Setup; 2023-06-18: Batch 1 Dev; 2023-06-25: Cleaning; 2023-11-12: MK-1167; 2023-11-19: MK-1167; 2023-11-26: MK-1167; 2023-12-03: MK-1167; 2023-12-10: MK-3543; 2023-12-17: MK-3543; 2023-12-24: MK-3543; 2023-12-31: MK-3543; 2024-01-08: Troubleshoot; 2024-01-15: MK-3543; 2024-01-22: Requal; 2024-01-29: MK-3543; 2024-02-05: MK-3543; 2024-02-12: Cleaning to potent; 2024-02-26: Troubleshoot, qual new springs, improvements; 2024-03-18: testing; 2024-03-25: Downtime; 2024-04-01: Downtime; 2024-04-08: Troubleshoot and Spring qual; 2024-04-22: MECH; 2024-04-29: Ranged Formulation testing; 2024-06-03: Mech improvement testing; 2024-06-24: Ionization testing; 2024-07-22: Ionization install; 2024-07-29: hold for doc; 2024-08-05: Bar dosator install; 2024-08-12: DDT FAT; 2024-08-26: Deduster; 2024-09-02: DDT arrives (earliest); 2024-09-16: Size OO; 2024-09-30: Size 4; 2024-10-07: Install & Automation; 2024-10-14: SAT; 2024-10-21: SAT; 2024-10-28: IOQ; 2024-11-04: Automation AOQ; 2024-11-11: AOQ; 2024-11-18: Move to 1212; 2024-11-25: AOQ; 2024-12-02: Drum dosing trolley testing; 2025-01-13: ModuC PQ; 2025-01-20: DDT PQ; 2025-01-27: Tamping pin PQ; 2025-02-10: MK-3543; 2025-02-17: MK-3543; 2025-03-03: consider 1708??; 2025-03-31: MK-3543; 2025-05-12: move to 1261; 2025-07-28: MK-1708 Autoencapsulation batches?; 2025-10-13: see potent
Manual Encapsulation (C ) | 2023-04-09: MK-8527 Setup; 2023-04-16: Dev; 2023-04-23: Batch 1; 2023-04-30: Cleaning; 2023-07-30: MK-8527 Setup; 2023-08-06: Batch 1; 2023-08-13: Cleaning; 2023-10-01: MK-8591; 2023-10-08: MK-8591; 2023-10-15: MK-8591; 2023-10-22: MK-8591; 2023-10-29: MK-8591; 2023-11-05: MK-8591; 2023-11-12: MK-8591; 2024-04-29: Setup; 2024-05-06: MK-4318 PBO dev; 2024-05-13: New ICAPS Qual; 2024-05-20: New ICAPS Qual; 2024-05-27: Clean; 2024-06-03: Clean; 2024-06-10: Setup; 2024-06-17: MK-8591 1mg; 2024-06-24: Clean; 2024-08-19: MK-6552 1MG; 2024-10-28: DFB turnaround; 2024-11-04: MK-6878; 2024-11-11: MK-6878; 2024-12-02: iCaps and Sade/Sejong CV; 2025-01-13: MK-4646; 2025-01-20: MK-4646; 2025-02-03: Clean; 2025-02-17: MK-3214; 2025-02-24: MK-3214; 2025-03-03: MK-3214; 2025-03-17: MOVE MANUAL ENCAPS to 1213; 2025-03-31: MK-1708 x4; 2025-04-07: MK-1708; 2025-04-14: MK-1708; 2025-04-21: MK-1708; 2025-04-28: MK-1708; 2025-05-12: MK-7526; 2025-05-19: MK-7526; 2025-05-26: MK-7526; 2025-07-28: MK-2828 3 batches 5-10k; early Aug preference
Spray Drying (D) | 2023-08-06: Spray Drying DoE; 2023-08-13: DoE week 2; 2023-08-20: DoE week 3; 2023-08-27: DoE week 4; 2023-09-03: MK-1084; 2023-09-10: MK-1084; 2023-09-17: MK-1084; 2023-09-24: MK-1084; 2023-10-01: MK-1084; 2023-10-08: Spray Dryer Testing; 2023-10-15: Spray Dryer Testing; 2023-10-22: Spray Dryer Testing; 2023-10-29: Spray Dryer Testing; 2023-11-05: Spray Dryer Shutdown; 2023-11-12: Spray Dryer Shutdown; 2023-11-19: Spray Dryer Shutdown; 2023-11-26: PMs; 2024-02-12: Spray Dryer Testing; 2024-02-19: Spray Dryer Testing; 2024-02-26: GES; 2024-03-04: Mech; 2024-03-11: GEA onsite; 2024-03-18: Spray Dryer Testing; 2024-03-25: Spray Dryer Testing; 2024-04-01: Spray Dryer Testing; 2024-04-08: Spray Dryer Testing; 2024-04-22: Spray Dryer Testing; 2024-04-29: Spray Dryer Testing; 2024-05-06: Spray Dry; 2024-05-13: Hold; 2024-05-20: Dev Clean; 2024-06-24: Tray dryer testing; 2024-07-29: GMP Clean; 2024-08-26: HMPCAS - two fluid - short; 2024-09-16: MK-7480 placebo dev batch; 2024-09-30: Clean and reset; 2024-10-07: Sanitization hold; 2024-10-21: Spray Dryer PM Shutdown; 2024-11-04: NaCap; 2024-11-11: NaCap; 2024-11-18: GMP Clean and reset; 2024-12-02: MK-6916; 2025-01-06: GMP Clean, sanitize, and reset; 2025-02-03: MK-6916; 2025-03-03: Sodium caprate and mannitol spray test; 2025-03-24: XXXX Development; 2025-04-14: XXXX Clinical Batch; 2025-05-19: GLP 1 spray?; 2025-05-26: GLP 1 spray?; 2025-06-02: GLP 1 spray?; 2025-06-09: GLP 1 spray?; 2025-06-16: GLP 1 spray?; 2025-06-23: GLP 1 spray?; 2025-06-30: GLP 1 spray?
Potent (E ) | 2024-01-29: EP-200 CV; 2024-02-05: EP-200CV; 2024-02-12: EP-200CV; 2024-02-19: Setup; 2024-02-26: Placebo batch 1; 2024-03-04: Placebo Batch2; 2024-03-11: Qualification; 2024-03-18: Testing Harro; 2024-03-25: Formulation testing; 2024-05-06: OEB 5 isolator testing/ICAPS; 2024-11-11: Potent setup; 2024-11-25: Setup; 2024-12-02: Dry run; 2025-02-24: B-5250 GMP; 2025-03-03: Minor Clean; 2025-03-10: B-5250 GMP; 2025-03-17: Minor Clean; 2025-03-24: B-5250 GMP; 2025-03-31: Cleaning; 2025-04-07: B-5250 Pkg; 2025-04-21: Cleaning; 2025-04-28: Results; 2025-05-05: Cleaning; 2025-05-12: Results; 2025-05-26: MK-2420; 2025-06-02: MK-2420; 2025-06-09: Cleaning; 2025-06-16: Results; 2025-06-23: Cleaning; 2025-06-30: Results; 2025-08-04: MK-0472; 2025-08-11: MK-0472; 2025-08-18: MK-0472; 2025-08-25: MK-0472; 2025-09-01: MK-0472; 2025-09-08: MK-0472; 2025-10-20: MK-2420; 2025-10-27: MK-2420; 2025-11-03: MK-2420; 2025-11-10: MK-2420
Autoinjector (F) | 2023-12-17: Arrival; 2024-01-15: Installation; 2024-01-22: SAT; 2024-01-29: SAT; 2024-03-25: PQ; 2024-04-01: PQ; 2024-04-08: AIQ; 2024-04-15: AIQ; 2024-05-06: Prep; 2024-05-13: Dev Batch; 2024-05-20: Turnaround; 2024-07-29: MK-7962Dev/ training batch; 2024-08-19: Setup; 2024-08-26: MK-7962 GMP batch; 2024-09-02: MK-7962 GMP batch; 2024-09-09: MK-7962 GMP batch; 2024-09-16: MK-7962 GMP batch; 2024-09-23: Cleaning; 2024-11-11: MRT Water; 2024-11-25: Setup; 2024-12-02: MK-7962 GMP batch; 2024-12-09: MK-7962 GMP batch; 2024-12-16: Cleaning; 2025-01-13: Exit calibration; 2025-01-20: Move Auto injector out, TSG in for SAT/IQ/OQ; 2025-03-24: Then XM12 with RC and PTM300? 1214 becomes Manual Encaps room, 1213 back to FC
Bottle Filling/Liquid (G) | 2023-12-10: Setup; 2023-12-17: Water testing; 2024-01-15: Cleaning; 2024-01-22: Dev batch; 2024-01-29: Reset; 2024-02-05: GMP batch; 2024-02-12: GMP batch; 2024-02-19: Cleaning; 2024-02-26: GMP batch; 2024-03-04: Cleaning; 2024-05-27: Setup; 2024-06-03: MK-1708 GMP batch; 2024-06-10: MK-1708 Batch 2; 2024-06-17: Cleaning; 2024-06-24: Cleaning
Other (H) | 2024-03-18: Setup; 2024-03-25: HME Automation Testing; 2024-04-01: HME PMs?; 2024-06-10: HME testing (Intern project); 2024-06-24: HME testing; 2024-07-29: Setup; 2024-08-05: Film coater; 2024-08-12: shake down; 2024-08-19: shakedown; 2024-09-09: Clean; 2024-09-16: MK-1084 FC PBO Dev; 2024-09-23: Cleaning; 2024-10-07: MK-1084 FC Dev; 2024-10-14: Clean; 2024-10-28: HME; 2024-11-04: HME; 2024-11-11: HME shakedown; 2025-03-03: Move FC to 1251, prep 1213 for manual encaps; 2025-09-22: MK-0616 PEDS w/ film coat
New equipment introduction | bar: 2024-02-26
Non processing activities (I) | 2024-02-26: MECO Skid work; 2024-03-25: Profill practice; 2024-04-01: Sporcleanz; 2024-05-13: 15-tours; 2024-05-20: 20-BYKTWD; 21-Safety standdown; 2024-05-27: 29-AH reg (1-3pm window); 2024-06-10: Safety Audit; 2024-07-22: Sade weight sorter investigation testing; 2024-07-29: Clean HME; 2024-08-05: Sejong Weight sorter IQ/OQ/AOQ; 2024-08-12: Hammermill CV; 2024-08-19: Russell Sieve; 2024-09-02: Move HME; 2025-01-13: MRT, TSG, HME - room and equip move plan
Process Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 6 | 6 | 6 | 6 | 5 | 4 | 4 | 4 | 4 | 3 | 4 | 3 | 3 | 4 | 2 | 3 | 3 | 4 | 3 | 4 | 5 | 5 | 5 | 6 | 5 | 5 | 4 | 6 | 7 | 7 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Patrick | 2024-01-08: E; 2024-01-15: E; 2024-01-22: E; 2024-01-29: E; 2024-02-05: E; 2024-02-12: E; 2024-02-19: E; 2024-02-26: E; 2024-03-04: E; 2024-03-11: E; 2024-03-18: E; 2024-04-01: H; 2024-04-08: H; 2024-04-15: H; 2024-04-22: H; 2024-06-10: E; 2024-06-17: E; 2024-06-24: E; 2024-07-01: E; 2024-07-08: E; 2024-07-15: E; 2024-07-22: E; 2024-07-29: B/A1; 2024-08-05: B/A1; 2024-08-12: B/A1; 2024-08-19: B/A1; 2024-08-26: B/A1; 2024-09-02: B/A1; 2024-09-09: B/A1; 2024-09-16: B/A1; 2024-09-23: B/A1; 2024-09-30: B/A1; 2024-10-07: B/A1; 2024-10-14: B/A1; 2024-10-21: B/A1; 2024-10-28: B/A1; 2024-11-04: B/A1; 2024-11-11: B/A1; 2024-11-18: B/A1; 2024-11-25: B/A1; 2024-12-02: B/A1; 2024-12-09: B/A1
Mike | 2024-01-08: A; 2024-01-15: A; 2024-01-22: A/G; 2024-01-29: A/G; 2024-02-05: A/G; 2024-02-12: A/G; 2024-02-19: A/G; 2024-04-22: C; 2024-04-29: C/A; 2024-05-06: C/A; 2024-05-13: C/A; 2024-05-20: C; 2024-05-27: C; 2024-06-03: C; 2024-06-10: C; 2024-06-17: C; 2024-06-24: C; 2024-07-01: C; 2024-07-08: G; 2024-07-15: G; 2024-07-22: G; 2024-07-29: G; 2024-08-05: G; 2024-08-12: G; 2024-08-19: G; 2024-08-26: G/I; 2024-09-02: G/I; 2024-09-09: I; 2024-09-16: I; 2024-09-23: I; 2024-09-30: C/I; 2024-10-07: C/I; 2024-10-14: C/I; 2024-10-21: C/I; 2024-10-28: C/I; 2024-11-04: I; 2024-11-11: A1/I; 2024-11-18: A1/I; 2024-11-25: A1/I; 2024-12-02: A1/I; 2024-12-09: A1/I
Sergio | bar: 2024-01-22 to 2024-04-22; 2024-05-20; 2024-07-01 to 2024-12-09
Rob | 2024-01-08: F; 2024-01-15: F; 2024-01-22: F; 2024-01-29: F; 2024-02-05: E,F; 2024-02-12: E,F; 2024-02-19: E,F; 2024-02-26: E,F; 2024-03-04: F; 2024-03-11: F; 2024-03-18: F; 2024-03-25: F; 2024-04-01: F; 2024-04-08: F; 2024-04-15: F; 2024-04-22: F; 2024-04-29: F; 2024-05-06: F; 2024-05-13: F; 2024-05-20: B; 2024-05-27: B; 2024-06-03: B; 2024-06-10: B; 2024-06-17: B; 2024-06-24: B; 2024-07-01: F; 2024-07-08: F; 2024-07-15: F; 2024-07-22: F; 2024-07-29: F; 2024-08-05: F; 2024-08-12: F; 2024-08-19: F; 2024-08-26: F; 2024-09-02: F; 2024-09-09: F; 2024-09-16: F/E; 2024-09-23: F/E; 2024-09-30: F/E; 2024-10-07: F/E; 2024-10-14: F/E; 2024-10-21: F/E; 2024-10-28: F/E; 2024-11-04: F/E; 2024-11-11: F/E; 2024-11-18: F/E; 2024-11-25: F/E; 2024-12-02: F/E; 2024-12-09: F/E
Syed | 2024-01-22: E; 2024-01-29: E; 2024-02-05: E; 2024-02-12: E; 2024-02-19: E, A; 2024-02-26: E, A; 2024-03-04: E, A; 2024-03-11: E, A; 2024-03-18: E, A; 2024-03-25: E, A; 2024-04-01: E, A
Joe | bar: 2024-01-15 to 2024-02-12; 2024-09-02 to 2024-12-09
James T | 2024-05-06: A; 2024-05-13: A; 2024-05-20: A/G; 2024-05-27: A/G; 2024-06-03: A/G; 2024-06-10: A/G; 2024-06-17: G; 2024-06-24: G; 2024-07-01: G; 2024-08-05: A2; 2024-08-12: A2; 2024-08-19: A2; 2024-08-26: A2; 2024-09-02: A2/D; 2024-09-09: A2/D; 2024-09-16: A2/D; 2024-09-23: A2/D; 2024-09-30: A2/D; 2024-10-07: A2/D; 2024-10-14: A2/D; 2024-10-21: A2/D; 2024-10-28: A2/D; 2024-11-04: A2/D; 2024-11-11: A2/D; 2024-11-18: A2/D; 2024-11-25: A2/D; 2024-12-02: A2/D; 2024-12-09: A2/D
Liam | bar: 2024-06-03 to 2024-07-01
Sadia | bar: 2024-07-29 to 2024-12-09
Gabriella | bar: 2024-09-02 to 2024-12-09
Jan | bar: 2024-07-08 to 2024-07-15; 2024-07-29 to 2024-12-09
Equipment | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 8 | 4 | 4 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 8 | 8 | 10 | 13 | 10 | 11 | 11 | 10 | 11 | 11 | 9 | 8 | 9 | 11 | 15 | 15 | 12 | 13 | 14 | 12 | 11 | 11 | 8 | 0 | 0 | 0 | 12 | 13 | 10 | 8 | 8 | 11 | 11 | 11 | 11 | 13 | 13 | 10 | 11 | 13 | 14 | 15 | 15 | 15 | 14 | 12 | 12 | 10 | 10 | 11 | 11 | 9 | 9 | 10 | 10 | 11 | 11 | 9 | 9 | 9
Utilization (out of 13 *major) | 2024-01-08: 0%; 2024-01-15: 15.38%; 2024-01-22: 38.46%; 2024-01-29: 61.54%; 2024-02-05: 61.54%; 2024-02-12: 76.92%; 2024-02-19: 100%; 2024-02-26: 76.92%; 2024-03-04: 84.62%; 2024-03-11: 84.62%; 2024-03-18: 76.92%; 2024-03-25: 84.62%; 2024-04-01: 84.62%; 2024-04-08: 69.23%; 2024-04-15: 61.54%; 2024-04-22: 69.23%; 2024-04-29: 84.62%; 2024-05-06: 115.4%; 2024-05-13: 115.4%; 2024-05-20: 92.31%; 2024-05-27: 100%; 2024-06-03: 107.7%; 2024-06-10: 92.31%; 2024-06-17: 84.62%; 2024-06-24: 84.62%; 2024-07-01: 61.54%; 2024-07-08: 0%; 2024-07-15: 0%; 2024-07-22: 0%; 2024-07-29: 92.31%; 2024-08-05: 100%; 2024-08-12: 76.92%; 2024-08-19: 61.54%; 2024-08-26: 61.54%; 2024-09-02: 84.62%; 2024-09-09: 84.62%; 2024-09-16: 84.62%; 2024-09-23: 84.62%; 2024-09-30: 100%; 2024-10-07: 100%; 2024-10-14: 76.92%; 2024-10-21: 84.62%; 2024-10-28: 100%; 2024-11-04: 107.7%; 2024-11-11: 115.4%; 2024-11-18: 115.4%; 2024-11-25: 115.4%; 2024-12-02: 107.7%; 2024-12-09: 92.31%; 2024-12-16: 92.31%; 2024-12-23: 76.92%; 2024-12-30: 76.92%; 2025-01-06: 84.62%; 2025-01-13: 84.62%; 2025-01-20: 69.23%; 2025-01-27: 69.23%; 2025-02-03: 76.92%; 2025-02-10: 76.92%; 2025-02-17: 84.62%; 2025-02-24: 84.62%; 2025-03-03: 69.23%; 2025-03-10: 69.23%; 2025-03-17: 69.23%
Blenders
LM-40 - VBE 1 (BN##)* | 2023-02-05: A; 2023-02-12: A; 2023-02-19: A; 2023-02-26: A; 2023-03-05: A; 2023-04-09: A; 2023-04-16: A; 2023-04-23: A; 2023-04-30: A; 2023-06-11: A; 2023-06-18: A; 2023-06-25: A; 2023-07-30: B; 2023-08-06: B; 2023-08-13: B; 2023-10-01: B; 2023-10-08: B; 2023-10-15: B; 2023-10-22: B; 2023-10-29: B; 2023-11-05: B; 2023-11-12: B; 2024-02-26: A; 2024-03-04: A; 2024-03-11: A; 2024-03-18: A; 2024-03-25: A; 2024-04-01: A; 2024-04-15: A; 2024-04-22: A; 2024-04-29: A; 2024-05-06: A; 2024-05-13: A; 2024-06-03: A2; 2024-06-10: A2; 2024-06-17: A2; 2024-06-24: A2; 2024-07-01: A2; 2024-09-02: A2; 2024-09-09: A2; 2024-09-16: A2; 2024-09-23: A2; 2024-09-30: A/C; 2024-10-07: C; 2024-10-14: C; 2024-10-21: C; 2024-10-28: C; 2024-11-04: A1; 2024-11-11: A1; 2024-11-18: A1; 2024-11-25: A1; 2024-12-02: A1; 2024-12-09: A1; 2024-12-16: A1; 2024-12-23: A1; 2024-12-30: A1; 2025-01-06: A1; 2025-01-13: A1; 2025-01-20: A1; 2025-01-27: A1; 2025-02-03: A1; 2025-02-10: A1; 2025-02-17: A1; 2025-02-24: A1; 2025-03-03: A1; 2025-03-10: A1; 2025-03-17: A1; 2025-03-24: A1; 2025-03-31: A1; 2025-04-07: A1
LM-40 - VBE 2 (BN##) | bar: 2024-04-29 to 2024-07-01
LM-40 - Isolator (BN##) | bar: 2024-01-29 to 2024-06-24; 2024-07-29 to 2024-12-16
PTM-300 (BN##)* | 2023-04-30: B; 2023-05-07: B; 2023-05-14: B; 2024-01-22: A; 2024-01-29: A; 2024-02-05: A; 2024-02-12: A; 2024-02-19: A; 2024-04-08: PM; 2024-04-15: A; 2024-04-22: A; 2024-04-29: A; 2024-05-06: A; 2024-05-13: A; 2024-05-20: A; 2024-05-27: A; 2024-06-03: A; 2024-06-10: A; 2024-06-17: A; 2024-06-24: A; 2024-07-01: A; 2024-07-29: A2; 2024-08-05: A2; 2024-08-12: A2; 2024-09-30: A1; 2024-10-07: A1; 2024-10-14: A1; 2024-10-21: A1; 2024-10-28: A1; 2024-11-04: A
Sieve | 2023-04-30: B; 2023-05-07: B; 2023-05-14: B; 2024-09-02: A2; 2024-09-09: A2; 2024-09-16: A2; 2024-09-23: A2; 2024-09-30: A2; 2024-10-07: A1; 2024-10-14: A1; 2024-10-21: A1; 2024-10-28: A1
Comill | bar: 2024-02-19 to 2024-06-24
Hammermill
RC* | 2023-04-30: B; 2023-05-07: B; 2023-05-14: B; 2024-01-22: A; 2024-01-29: A; 2024-02-05: A; 2024-02-12: A; 2024-02-19: A; 2024-02-26: A; 2024-03-04: A; 2024-03-11: A; 2024-03-18: A; 2024-03-25: A; 2024-04-01: A; 2024-04-29: PM; 2024-05-06: A; 2024-05-13: A; 2024-05-20: A; 2024-05-27: A; 2024-06-03: A; 2024-06-10: A; 2024-06-17: A; 2024-06-24: A; 2024-07-01: A; 2024-09-02: A2; 2024-09-09: A2; 2024-09-16: A2; 2024-09-23: A2; 2024-09-30: A2; 2024-10-07: A2; 2024-11-04: A1; 2024-11-11: A1; 2024-11-18: A1; 2024-11-25: A1; 2024-12-02: A1; 2024-12-09: A1; 2024-12-16: A1; 2024-12-23: A1; 2024-12-30: A1; 2025-01-06: A1; 2025-01-13: A1; 2025-01-20: A1; 2025-01-27: A1; 2025-02-03: A1; 2025-02-10: A1; 2025-02-17: A1; 2025-02-24: A1; 2025-03-03: A1; 2025-03-10: A1; 2025-03-17: A1; 2025-03-24: A1; 2025-03-31: A1; 2025-04-07: A1
RC 2
XL-100* | 2023-04-30: B; 2023-05-07: B; 2023-05-14: B; 2024-01-22: A; 2024-01-29: A; 2024-02-05: A; 2024-02-12: A; 2024-02-19: A; 2024-02-26: A; 2024-03-04: A; 2024-03-11: A; 2024-03-18: A; 2024-03-25: A; 2024-04-01: A; 2024-04-08: PM; 2024-04-22: PM; 2024-05-06: A; 2024-05-13: A; 2024-05-20: A; 2024-05-27: A; 2024-06-03: A; 2024-06-10: A; 2024-08-05: A1; 2024-08-26: A1; 2024-09-30: A1; 2024-10-07: A1; 2024-10-14: A1; 2024-10-21: A1; 2024-10-28: A1; 2024-11-04: A1; 2024-11-11: A1; 2024-11-18: A1; 2024-11-25: A1; 2024-12-02: A1; 2024-12-09: A1; 2024-12-16: A1; 2024-12-23: A1; 2024-12-30: A1; 2025-01-06: A1; 2025-01-13: A1; 2025-01-20: A1; 2025-01-27: A1; 2025-02-03: A1; 2025-02-10: A1; 2025-02-17: A1; 2025-02-24: A1; 2025-03-03: A1; 2025-03-10: A1; 2025-03-17: A1; 2025-03-24: A1; 2025-03-31: A1; 2025-04-07: A1
XM-12* | 2024-03-04: MOVE IN XM12; 2024-03-11: HEPA; 2024-04-01: PM; 2024-05-06: A2; 2024-05-13: A2; 2024-05-20: A2; 2024-05-27: A2; 2024-06-03: A2; 2024-06-10: A2; 2024-06-17: A2; 2024-06-24: A2; 2024-07-01: A2; 2024-07-29: A2; 2024-08-05: A2; 2024-08-12: A2; 2024-08-19: A2; 2024-09-02: A2; 2024-09-09: A2; 2024-09-16: A2; 2024-09-23: A2; 2024-09-30: A2; 2024-10-07: A2
Film Coater* | bar: 2024-07-29 to 2024-10-07; 2025-01-06 to 2025-02-24
Profill 1* | 2023-04-09: A; 2023-04-16: A; 2023-04-23: A; 2023-04-30: A; 2023-07-30: B; 2023-08-06: B; 2023-08-13: B; 2023-10-01: B; 2023-10-08: B; 2023-10-15: B; 2023-10-22: B; 2023-10-29: B; 2023-11-05: B; 2023-11-12: B; 2024-05-06: C; 2024-05-13: C; 2024-05-20: C; 2024-05-27: C; 2024-06-03: C; 2024-06-10: C; 2024-06-17: C; 2024-06-24: C; 2024-07-01: C; 2024-10-28: C; 2024-11-04: C; 2024-11-11: C; 2024-11-18: C; 2024-11-25: C; 2024-12-02: C
Profill 2
Harro* | 2023-02-05: A; 2023-02-12: A; 2023-02-19: A; 2023-02-26: A; 2023-03-05: A; 2023-06-11: A; 2023-06-18: A; 2023-06-25: A; 2024-02-19: MOVE TO 1261; 2024-07-29: B; 2024-08-05: B; 2024-08-12: B; 2024-08-19: B; 2024-08-26: B; 2024-09-02: B; 2024-09-09: B; 2024-09-16: B; 2024-09-23: B; 2024-09-30: B; 2024-10-07: B; 2024-10-14: B; 2024-10-21: B; 2024-10-28: B; 2024-11-04: B; 2024-11-11: B; 2024-11-18: B; 2024-11-25: B; 2024-12-02: B; 2024-12-09: B; 2024-12-16: B; 2024-12-23: B; 2024-12-30: B; 2025-01-06: B; 2025-01-13: B; 2025-01-20: B; 2025-01-27: B; 2025-02-03: B; 2025-02-10: B; 2025-02-17: B; 2025-02-24: B; 2025-03-03: B; 2025-03-10: B; 2025-03-17: B; 2025-03-24: B; 2025-03-31: B; 2025-04-07: B; 2025-04-14: B; 2025-04-21: B; 2025-04-28: B; 2025-05-05: E; 2025-05-12: E; 2025-05-19: E; 2025-05-26: E; 2025-06-02: E; 2025-06-09: E; 2025-06-16: E; 2025-06-23: E; 2025-06-30: E
Icaps | 2023-02-05: A; 2023-02-12: A; 2023-02-19: A; 2023-02-26: A; 2023-03-05: A; 2023-04-09: A; 2023-04-16: A; 2023-04-23: A; 2023-04-30: A; 2023-07-30: B; 2023-08-06: B; 2023-08-13: B; 2023-10-01: B; 2023-10-08: B; 2023-10-15: B; 2023-10-22: B; 2023-10-29: B; 2023-11-05: B; 2023-11-12: B; 2024-01-29: B; 2024-02-05: E; 2024-02-12: E; 2024-02-19: E; 2024-05-06: C; 2024-05-13: C; 2024-05-20: C; 2024-05-27: C; 2024-06-03: C; 2024-06-10: C; 2024-06-17: C; 2024-06-24: C; 2024-07-01: C; 2024-11-11: E; 2024-11-18: E; 2024-11-25: E; 2024-12-02: E; 2024-12-09: E; 2024-12-16: E; 2024-12-23: E; 2024-12-30: E; 2025-01-06: E; 2025-01-13: E; 2025-02-17: E; 2025-02-24: E; 2025-03-03: E; 2025-03-10: E; 2025-03-17: E; 2025-03-24: E; 2025-03-31: E; 2025-04-07: E; 2025-04-14: E; 2025-04-21: E; 2025-04-28: E; 2025-05-05: E; 2025-05-12: E; 2025-05-19: E; 2025-05-26: E; 2025-06-02: E; 2025-06-09: E; 2025-06-16: E; 2025-06-23: E; 2025-06-30: E
Short ICAPS | bar: 2024-07-29 to 2024-08-05; 2024-10-28 to 2025-06-09
Sade Weight Sorter | 2023-02-05: A; 2023-02-12: A; 2023-02-19: A; 2023-02-26: A; 2023-03-05: A; 2023-04-09: A; 2023-04-16: A; 2023-04-23: A; 2023-04-30: A; 2023-07-30: B; 2023-08-06: B; 2023-08-13: B; 2023-10-01: B; 2023-10-08: B; 2023-10-15: B; 2023-10-22: B; 2023-10-29: B; 2023-11-05: B; 2023-11-12: B; 2024-02-19: E; 2024-02-26: E; 2024-03-04: E; 2024-03-11: E; 2024-03-18: E; 2024-03-25: E; 2024-04-01: E; 2024-04-08: E; 2024-04-15: E; 2024-04-22: E; 2024-04-29: E; 2024-05-06: E; 2024-05-13: E; 2024-05-20: E; 2024-05-27: E; 2024-06-03: C; 2024-06-10: C; 2024-06-17: C; 2024-06-24: C; 2024-07-01: C; 2024-07-29: B; 2024-08-05: B; 2024-08-12: B; 2024-08-19: B; 2024-08-26: B; 2024-09-02: B; 2024-09-09: B; 2024-09-16: B; 2024-09-23: B; 2024-09-30: B; 2024-10-07: B; 2024-10-14: B; 2024-10-21: B; 2024-10-28: C; 2024-11-04: C; 2024-11-11: C; 2024-11-18: C; 2024-11-25: C
Sejong Weight Sorter 2 | bar: 2024-09-30 to 2024-10-21; 2024-11-11 to 2024-12-16; 2025-02-03 to 2025-04-28
Spray Dryer* | bar: 2023-07-30 to 2023-11-26; 2024-02-12 to 2024-06-03; 2024-07-29 to 2025-03-17
50L Tank | bar: 2024-01-15 to 2024-02-19; 2024-07-29 to 2024-08-12
20, 100 L tanks | bar: 2024-02-12 to 2024-06-03; 2024-07-29 to 2025-02-24
HME* | 2024-03-25: HME audit trail automation; 2024-07-29: I; 2024-08-05: I; 2024-10-21: H; 2024-10-28: H; 2024-11-04: H; 2024-11-11: H; 2024-11-18: H; 2024-11-25: H; 2024-12-02: H
Isolators* | bar: 2024-01-29 to 2024-05-13; 2024-05-27 to 2024-06-24; 2024-10-28 to 2025-03-24
Autoinjector* (MRT) | bar: 2024-01-15 to 2024-04-08; 2024-04-29 to 2024-05-13; 2024-07-29 to 2024-09-23; 2024-11-04 to 2025-01-13
TSG | bar: 2025-01-27 to 2025-03-31
Rooms | 2024-01-08: 11.11%; 2024-01-15: 77.78%; 2024-01-22: 66.67%; 2024-01-29: 88.89%; 2024-02-05: 88.89%; 2024-02-12: 100%; 2024-02-19: 66.67%; 2024-02-26: 66.67%; 2024-03-04: 77.78%; 2024-03-11: 88.89%; 2024-03-18: 77.78%; 2024-03-25: 66.67%; 2024-04-01: 44.44%; 2024-04-08: 55.56%; 2024-04-15: 55.56%; 2024-04-22: 66.67%; 2024-04-29: 77.78%; 2024-05-06: 100%; 2024-05-13: 114.3%; 2024-05-20: 100%; 2024-05-27: 71.43%; 2024-06-03: 57.14%; 2024-06-10: 57.14%; 2024-06-17: 57.14%; 2024-06-24: 57.14%; 2024-07-01: 57.14%; 2024-07-29: 80%; 2024-08-05: 70%; 2024-08-12: 70%; 2024-08-19: 50%; 2024-08-26: 60%; 2024-09-02: 90%; 2024-09-09: 90%; 2024-09-16: 90%; 2024-09-23: 90%; 2024-09-30: 90%; 2024-10-07: 90%; 2024-10-14: 70%; 2024-10-21: 80%; 2024-10-28: 90%; 2024-11-04: 70%; 2024-11-11: 90%; 2024-11-18: 90%; 2024-11-25: 100%; 2024-12-02: 80%; 2024-12-09: 90%; 2024-12-16: 90%; 2024-12-23: 0%; 2024-12-30: 0%; 2025-01-06: 90%; 2025-01-13: 80%; 2025-01-20: 80%; 2025-01-27: 90%; 2025-02-03: 80%; 2025-02-10: 90%; 2025-02-17: 90%; 2025-02-24: 80%; 2025-03-03: 60%; 2025-03-10: 60%; 2025-03-17: 50%; 2025-03-24: 40%; 2025-03-31: 40%; 2025-04-07: 30%; 2025-04-14: 10%; 2025-04-21: 10%; 2025-04-28: 10%; 2025-05-05: 0%; 2025-05-12: 0%; 2025-05-19: 0%; 2025-05-26: 0%; 2025-06-02: 0%; 2025-06-09: 0%; 2025-06-16: 0%; 2025-06-23: 0%
1211 | bar: 2024-01-15 to 2024-03-25; 2024-04-22 to 2024-06-10; 2024-08-05; 2024-08-26; 2024-09-30 to 2024-10-28; 2024-11-11 to 2024-12-16; 2025-01-06 to 2025-04-07
1212 | bar: 2024-01-08 to 2024-02-12; 2024-03-11 to 2024-05-20; 2024-07-29 to 2024-08-12; 2024-09-02 to 2024-10-07; 2024-11-11 to 2024-12-16; 2025-01-06 to 2025-04-28
1213 | 2024-01-15: G; 2024-01-22: G; 2024-01-29: G; 2024-02-05: G; 2024-02-12: G; 2024-02-19: G; 2024-07-29: H; 2024-08-05: H; 2024-08-12: H; 2024-08-19: H; 2024-08-26: H; 2024-09-02: H; 2024-09-09: H; 2024-09-16: H; 2024-09-23: H; 2024-09-30: H; 2024-10-07: H; 2024-10-14: H; 2025-01-06: A1; 2025-01-13: A1; 2025-01-20: A1; 2025-01-27: A1; 2025-02-03: A1; 2025-02-10: A1; 2025-02-17: A1; 2025-02-24: A1
1214 | 2024-01-15: A; 2024-01-22: A; 2024-01-29: A; 2024-02-05: A; 2024-02-12: A; 2024-02-19: A; 2024-02-26: A; 2024-03-04: A; 2024-03-11: A; 2024-03-18: A; 2024-03-25: A; 2024-04-29: A; 2024-05-06: A; 2024-05-13: A; 2024-05-20: A; 2024-05-27: A; 2024-06-03: A2; 2024-06-10: A2; 2024-06-17: A2; 2024-06-24: A2; 2024-07-01: A2; 2024-09-02: A2; 2024-09-09: A2; 2024-09-16: A2; 2024-09-23: A2; 2024-09-30: A2/A1; 2024-10-07: A1; 2024-10-14: A1; 2024-10-21: A1; 2024-10-28: A1; 2024-11-11: A1; 2024-11-18: A1; 2024-11-25: A1; 2024-12-02: A1; 2024-12-09: A1; 2024-12-16: A1; 2025-01-06: A1; 2025-01-13: A1; 2025-01-20: A1; 2025-01-27: A1; 2025-02-03: A1; 2025-02-10: A1; 2025-02-17: A1; 2025-02-24: A1; 2025-03-03: A1; 2025-03-10: A1; 2025-03-17: A1; 2025-03-24: A1; 2025-03-31: A1; 2025-04-07: A1
1215 | bar: 2024-02-12 to 2024-04-22; 2024-07-29 to 2024-12-16; 2025-01-06 to 2025-03-17
1233 | 2024-05-13: A; 2024-05-20: B; 2024-05-27: A; 2024-06-17: A2; 2024-06-24: C; 2024-07-01: A2; 2024-08-12: A2; 2024-09-02: H; 2024-09-09: A2; 2024-09-16: D; 2024-09-23: A2; 2024-09-30: D; 2024-10-07: A2; 2024-10-21: A1; 2024-10-28: B; 2024-11-04: C; 2024-11-18: D; 2024-11-25: C; 2024-12-09: A1; 2024-12-16: D; 2025-01-06: D; 2025-01-27: C; 2025-02-10: D; 2025-02-17: A1; 2025-02-24: A1/B; 2025-03-03: B; 2025-03-10: C; 2025-03-17: D; 2025-03-24: A1; 2025-03-31: A1
1241 | 2024-01-15: A; 2024-01-22: A; 2024-01-29: A; 2024-02-05: A; 2024-02-12: A; 2024-03-04: 1167 closeout; 2024-03-11: PM - DFB; 2024-07-29: I; 2024-09-02: A2; 2024-09-09: A2; 2024-09-16: A2; 2024-09-23: A1; 2024-09-30: A1; 2024-10-28: C; 2024-11-04: C; 2024-11-11: C; 2024-11-18: C; 2024-11-25: C; 2024-12-02: C; 2024-12-09: C; 2024-12-16: C
1242 | bar: 2024-01-15 to 2024-05-13; 2024-06-24 to 2024-07-01; 2024-07-29 to 2024-11-11; 2024-11-25 to 2024-12-16; 2025-01-06 to 2025-02-24
1261 | bar: 2024-01-29 to 2024-06-17; 2024-07-29 to 2024-12-16; 2025-01-06 to 2025-02-17
1262 | bar: 2024-04-08 to 2024-05-20; 2024-07-29 to 2024-09-23; 2024-10-21 to 2024-11-25
1263 | 2024-01-15: B; 2024-01-29: B; 2024-02-05: B; 2024-02-12: B; 2024-02-26: E; 2024-03-04: E; 2024-03-11: E; 2024-03-18: E; 2024-04-29: C; 2024-05-06: C; 2024-05-13: C; 2024-05-20: C; 2024-05-27: C; 2024-06-03: C; 2024-06-10: C; 2024-06-17: C; 2024-06-24: C; 2024-07-01: C; 2024-07-29: I; 2024-10-07: C; 2024-10-14: C; 2024-10-21: C; 2024-10-28: C; 2024-11-04: C; 2024-11-11: C; 2024-11-18: C; 2024-11-25: C; 2024-12-02: C; 2024-12-09: C; 2024-12-16: C; 2025-01-06: C; 2025-01-13: C; 2025-01-20: C; 2025-01-27: C; 2025-02-03: C; 2025-02-10: C; 2025-02-17: C; 2025-02-24: C; 2025-03-03: C; 2025-03-10: C
VBEs
1
2
3
LM40 Blender VBE #4 | 2024-02-26: 1214; 2024-04-15: 1214; 2024-04-29: 1263
5
Manual Encap 1 of 2 #6 | 2024-02-26: 1263; 2024-04-15: 1263
Manual Encap 2 of 2 # 7 | 2024-02-26: 1263; 2024-04-15: 1263
8
Solvent 9 | 2024-02-26: 1261; 2024-04-15: 1261
10
Large, well vert space 11 | 2024-02-26: OOS/1251; 2024-04-15: OOS/1251
Large, cont liner, vert space 12 | 2024-02-26: 1213; 2024-04-15: 1213
LM40 Blender 13, OOS | 2024-02-26: 1263; 2024-04-15: 1262; 2024-04-29: 1251
Small IPC 16 | 2024-02-26: 1211; 2024-04-15: 1211
Note on CV10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6kg batches, LM40/VBE sieve
Note on DI10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RC
Note on DX10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6 batches, small, includes RC, film coat Reply: 10mg dose, changing FDC; low and high 0616; low/high disintegrant - Reply: Current bottleneck is 1213 and FC vs PODs and 1708 Reply: Discuss major clean strategy
Note on BP12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: End: 26Apr Michelle, Wesley, Ray (Jan if available)
Note on BS12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Blending Start: 29Apr Blending End: 03May Encapsulation Start: 06May Encapsulation End: 31May Michelle, Wesley, Ray (Jan if available)
Note on BX12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test bar dosator, wider outlet, and empty capsule discharge Start: 03Jun End: 28Jun Michelle, Wesley, Ray (Jan if available)
Note on CH12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DDT FAT
Note on CP12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Install and commissioning, automation
Note on DH13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will have to be in 1263 as film coating needed for 8527
Note on DI13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Go/No-Go in Dec 2024 Reply: ~1000 each dose and stable humidity control
Note on DO13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update mid-Oct once DCT forms Reply: 2 potencies; 15k & 10k worst case
Note on DU13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tight timelines if any previous slip Reply: Would optimistically fit into 3214 if a no-go
Note on DV13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tight timelines if any previous slip Reply: Would optimistically fit into 3214 if a no-go
Note on DW13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tight timelines if any previous slip Reply: Would optimistically fit into 3214 if a no-go
Note on DK14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Forecasting needed
Note on DI15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Refresh schedule with day-for-day plan and Dec test batch experience
Note on DW15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 batches, may be more than 2 Reply: More info to come in Nov Reply: >10k prefer autoencaps
Note on A36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://collaboration.merck.com/sites/FLExCenter2/Shared%20Documents/Oral%20Solid%20Dosage/Facility/Master%20Equipment%20List.xlsx?web=1
Note on A79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://mydrive.merck.com/personal/clancjam_merck_com/Documents/documents/PharmOps/OSD%20Supervisor%20Activities/Communications/FLEx%20OSD%20VBEs.pptx?web=1

## subset
[37 empty] | number of process | process engineers | equipment utilization
2.375
[37 empty] | 3.5333 | 5.7333 | 0.73077
Week starting | time axis 2023-01-01 to 2024-02-12
ISO week | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 2 | 3 | 4 | 5 | 6 | 7
Process | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 1 | 2 | 4 | 2 | 2 | 2 | 3 | 4 | 5 | 4 | 5
Tablet Compression (A1) - XL100 | 2023-04-30: MK-1084 Setup; 2023-05-07: Batch 1; 2023-05-14: Cleaning; 2023-07-02: Holiday; 2023-07-09: Shutdown; 2023-07-16: Shutdown; 2023-07-23: Shutdown; 2023-07-30: Bringup; 2023-12-17: MK-1084 setup; 2023-12-24: Holiday; 2023-12-31: Shutdown; 2024-01-08: Bringup; 2024-01-22: MK-1084; 2024-01-29: MK-1084; 2024-02-05: MK-1084; 2024-02-12: MK-1084
Tablet Compression (A2) - XM12
Autoencapsulator (B) | 2023-02-05: MK-1942 Setup; 2023-02-12: Dev; 2023-02-19: Batch 1; 2023-02-26: Batch 2; 2023-03-05: Cleaning; 2023-06-11: MK-1167 Setup; 2023-06-18: Batch 1 Dev; 2023-06-25: Cleaning; 2023-11-12: MK-1167; 2023-11-19: MK-1167; 2023-11-26: MK-1167; 2023-12-03: MK-1167; 2023-12-10: MK-3543; 2023-12-17: MK-3543; 2023-12-24: MK-3543; 2023-12-31: MK-3543; 2024-01-08: Troubleshoot; 2024-01-15: MK-3543; 2024-01-22: Requal; 2024-01-29: MK-3543; 2024-02-05: MK-3543; 2024-02-12: Cleaning to potent
Manual Encapsulation (C ) | 2023-04-09: MK-8527 Setup; 2023-04-16: Dev; 2023-04-23: Batch 1; 2023-04-30: Cleaning; 2023-07-30: MK-8527 Setup; 2023-08-06: Batch 1; 2023-08-13: Cleaning; 2023-10-01: MK-8591; 2023-10-08: MK-8591; 2023-10-15: MK-8591; 2023-10-22: MK-8591; 2023-10-29: MK-8591; 2023-11-05: MK-8591; 2023-11-12: MK-8591
Spray Drying (D) | 2023-08-06: Spray Drying DoE; 2023-08-13: DoE week 2; 2023-08-20: DoE week 3; 2023-08-27: DoE week 4; 2023-09-03: MK-1084; 2023-09-10: MK-1084; 2023-09-17: MK-1084; 2023-09-24: MK-1084; 2023-10-01: MK-1084; 2023-10-08: Spray Dryer Testing; 2023-10-15: Spray Dryer Testing; 2023-10-22: Spray Dryer Testing; 2023-10-29: Spray Dryer Testing; 2023-11-05: Spray Dryer Shutdown; 2023-11-12: Spray Dryer Shutdown; 2023-11-19: Spray Dryer Shutdown; 2023-11-26: PMs; 2024-02-12: Spray Dryer Testing
Potent (E ) | 2024-01-29: EP-200 CV; 2024-02-05: EP-200CV; 2024-02-12: EP-200CV
Autoinjector (F) | 2023-12-17: Arrival; 2024-01-15: Installation; 2024-01-22: SAT; 2024-01-29: SAT
Bottle Filling/Liquid (G) | 2023-12-10: Setup; 2023-12-17: Water testing; 2024-01-15: Cleaning; 2024-01-22: Dev batch; 2024-01-29: Reset; 2024-02-05: GMP batch; 2024-02-12: GMP batch
Other (H)
New equipment introduction
Non processing activities (I)
weeks | [35 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Engineers | [35 empty] | 8 | 5 | 7 | 6 | 6 | 6 | 6 | 7 | 7 | 6 | 4 | 6 | 4 | 4 | 4
0-Patrick | [35 empty] | 3-B/11-A1 | 3-B | 3-B | 3-B | 4-B |  |  |  | 2-B | 2-B/5-B | 2-B/6-B | 2-B | 7-B/12-A1 | 7-B | 8-B/12-A1
1-Mike | [35 empty] | 18-G | 19-G | 1-C/20-G | 1-C | 1-C/21-G | 1-C/22-G | 1-C | 1-C | 1-C | 1-C |  | 12-A1/23-G | 12-A1/24-G
2-Sergio | [35 empty] | 9-D | 9-D | 9-D | 9-D | 10-D | 10-D | 10-D | 10-D | 10-D | 10-D | 10-D | 10-D |  |  | 12-A1/13-D
3-Rob | [35 empty] | 0: 15-F; 2: 16-F; 5: 14-E; 6: 14-E; 7: 14-E/17-F; 8: 17-F
4-Syed | [35 empty] | 0: 11-A1; 5: 14-E; 6: 14-E; 7: 14-E; 13: 12-A1
5-Joe | [35 empty] | 3-B/15-F | 3-B | 3-B/16-F | 3-B | 4-B |  |  | 17-F | 2-B/17-F | 2-B/5-B | 2-B/6-B | 2-B | 7-B | 7-B | 8-B
6-James T | [35 empty] | 9-D/18-G | 9-D/19-G | 9-D/20-G | 9-D | 10-D/21-G | 10-D/22-G | 10-D | 10-D | 10-D | 10-D | 10-D | 10-D/23-G | 24-G |  | 13-D
7-Liam | [35 empty] | 0: 11-A1; 11: 12-A1; 13: 12-A1
8-Sadia
9-Gabriella | [35 empty] | 2: 1-C; 3: 1-C; 4: 1-C; 5: 1-C; 6: 1-C; 7: 1-C; 8: 1-C; 9: 1-C
2024-01-10
Process | [35 empty] | 5 | 3 | 5 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 3 | 4 | 3 | 2 | 3
Tablet Compression (A1) - XL100 | [35 empty] | 0: MK-1084 setup; 11: MK-1084; 12: MK-1084; 13: MK-1084; 14: MK-1084
Tablet Compression (A2) - XM12
Autoencapsulator (B) | [35 empty] | 9: MK-3543; 10: Requal; 12: MK-3543; 13: MK-3543; 14: Cleaning to potent
Autoencapsulator (B) | [35 empty] | MK-3543 | MK-3543 | MK-3543 | MK-3543 | Troubleshoot |  |  |  | MK-1167 | MK-1167 | MK-1167 | MK-1167
Manual Encapsulation (C ) | [35 empty] | 2: MK-8591; 3: MK-8591; 4: MK-8591; 5: MK-8591; 6: MK-8591; 7: MK-8591; 8: MK-8591
Spray Drying (D) | [35 empty] | MK-1084 | MK-1084 | MK-1084 | MK-1084 | MK-1084 | MK-1084 | MK-1084 | MK-1084 | MK-1084 | MK-1084 | MK-1084 | MK-1084 |  |  | MK-1084
Potent (E ) | [35 empty] | 5: EP-200 CV; 6: EP-200CV; 7: EP-200CV
Autoinjector (F) | [35 empty] | 0: Arrival; 2: Installation; 7: SAT; 8: SAT
Bottle Filling/Liquid (G) | [35 empty] | 0: Setup; 1: Water testing; 2: Cleaning; 4: Dev batch; 5: Reset; 11: GMP batch; 12: GMP batch
Other (H)
New equipment introduction
Non processing activities (I)
Equipment
Utilization (out of 13 *major) | [35 empty] | 0.96154 | 0.5 | 0.80769 | 0.73077 | 0.76923 | 0.57692 | 0.53846 | 0.57692 | 0.76923 | 0.73077 | 0.46154 | 0.92308 | 0.88462 | 0.84615 | 0.88462
[36 empty] | 25 | 13 | 21 | 19 | 20 | 15 | 14 | 15 | 20 | 19 | 12 | 24 | 23 | 22 | 23
LM-40 - VBE 1 (BN##)* | bar: 0 to 4; 8 to 14
LM-40 - VBE 2 (BN##)
LM-40 - Isolator (BN##) | bar: 0 to 14
PTM-300 (BN##)* | bar: 0 to 4; 8 to 14
Sieve | bar: 0 to 4; 8 to 14
Comill | bar: 5 to 7
Hammermill
RC* | bar: 0 to 4; 8 to 14
RC 2
XL-100* | bar: 0 to 4; 8 to 14
XM-12*
Film Coater*
Profill 1* | bar: 0 to 4; 8 to 14
Profill 2
Harro* | bar: 0 to 14
Icaps | bar: 0 to 14
Short ICAPS
Sade Weight Sorter | bar: 0 to 14
Sejong Weight Sorter 2 | bar: 0 to 4; 8 to 14
Spray Dryer* | bar: 0 to 11; 14
50L Tank | bar: 0 to 2; 4 to 5; 11 to 12
20, 100 L tanks
HME*
Isolators* | bar: 5 to 7
Autoinjector* (MRT) | bar: 0; 2; 7 to 8
TSG
LM-40 - VBE 1 (BN##)* | bar: 0; 2 to 9; 11 to 14
LM-40 - VBE 2 (BN##)
LM-40 - Isolator (BN##)
PTM-300 (BN##)* | bar: 0; 11 to 14
Sieve | bar: 0; 11 to 14
Comill
Hammermill
RC* | bar: 0; 11 to 14
RC 2
XL-100* | bar: 0; 11 to 14
XM-12*
Film Coater* | bar: 0; 2 to 9; 11 to 14
Profill 1* | bar: 0; 11 to 14
Profill 2
Harro* | bar: 0; 2 to 9; 11 to 14
Icaps | bar: 0; 2 to 9; 11 to 14
Short ICAPS | bar: 2 to 9
Sade Weight Sorter | bar: 0; 2 to 9; 11 to 14
Sejong Weight Sorter 2
Spray Dryer* | bar: 0; 11 to 14
50L Tank | bar: 2 to 9
20, 100 L tanks
HME*
Isolators*
Autoinjector* (MRT)
TSG

## draft1_list-1204
task-index | task-name | processing-time(weeks) | engineers | rooms | LM-40 - VBE 1 (BN##)* | LM-40 - VBE 2 (BN##) | LM-40 - Isolator (BN##) | PTM-300 (BN##)* | Sieve | Comill | Hammermill | RC* | RC 2 | XL-100* | XM-12* | Film Coater* | Profill 1* | Profill 2 | Harro* | Icaps | Short ICAPS | Sade Weight Sorter | Sejong Weight Sorter 2 | Spray Dryer* | 50L Tank | 20, 100 L tanks | HME* | Isolators* | Autoinjector* (MRT) | TSG | 0-Patrick | 1-Mike | 2-Sergio | 3-Rob | 4-Syed | 5-Joe | 6-James T | 7-Liam | 8-Sadia | 9-Gabriella | 10-Jan
0 | start-0 | 0 | 0 | 0
1 | MK-8591-C | 7 | 2 | 1 | 1 | 1 | [10 empty] | 1 |  |  | 1 | 1 | 1 | 1 |  |  | 1 | [5 empty] | 1 | [7 empty] | 1
2 | MK-1167-B | 4 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 1
3 | MK-3543-1-B | 4 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 1
4 | MK-3543-TroubleShooting-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 1
5 | MK-3543-2-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 1
6 | MK-3543-Requal-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 1
7 | MK-3543-3-B | 2 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 1
8 | MK-3543-Cleaning-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 1
9 | MK-1084GMP-D | 4 | 2 | 1 | [19 empty] | 1 | [8 empty] | 1 |  |  |  | 1
10 | MK-1084Dev-D | 8 | 2 | 1 | [19 empty] | 1 | [8 empty] | 1 |  |  |  | 1
11 | MK-1084Setup-A1 | 1 | 2 | 1 | 1 |  |  | 1 | 1 |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 | [6 empty] | 1 | 1 | 1 |  | 1 |  | 1 | 1
12 | MK-1084-A1 | 4 | 2 | 1 | 1 |  |  | 1 | 1 |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 | [6 empty] | 1 | 1 | 1 |  | 1 |  | 1 | 1
13 | MK-1084-2-D | 1 | 2 | 1 | [19 empty] | 1 | [8 empty] | 1 |  |  |  | 1
14 | EP-200-E | 3 | 2 | 1 |  |  | 1 |  |  | 1 | [8 empty] | 1 | 1 |  | 1 | [5 empty] | 1 | [5 empty] | 1 | 1
15 | Arrival-F | 1 | 2 | 1 | [24 empty] | 1 |  |  |  |  | 1 |  | 1
16 | Installation-F | 1 | 2 | 1 | [24 empty] | 1 |  |  |  |  | 1 |  | 1
17 | SAT-F | 2 | 2 | 1 | [24 empty] | 1 |  |  |  |  | 1 |  | 1
18 | Setup-G | 1 | 2 | 1 | [20 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
19 | WaterTesting-G | 1 | 2 | 1 | [20 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
20 | Cleaning-G | 1 | 2 | 1 | [20 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
21 | Dev-G | 1 | 2 | 1 | [20 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
22 | Reset-G | 1 | 2 | 1 | [20 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
23 | GMP-G | 2 | 2 | 1 | [20 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
24 | end-0 | 0 | 0 | 0

## optimized-1204
| s | f | Start_Date | Finish_Date
start-0 | 0 | 0 | 2023-09-03 | 2023-09-03
MK-8591-C | 2 | 9 | 2023-09-17 | 2023-11-05
MK-1167-B | 8 | 12 | 2023-10-29 | 2023-11-26
MK-3543-1-B | 0 | 4 | 2023-09-03 | 2023-10-01
MK-3543-TroubleShooting-B | 4 | 5 | 2023-10-01 | 2023-10-08
MK-3543-2-B | 9 | 10 | 2023-11-05 | 2023-11-12
MK-3543-Requal-B | 10 | 11 | 2023-11-12 | 2023-11-19
MK-3543-3-B | 12 | 14 | 2023-11-26 | 2023-12-10
MK-3543-Cleaning-B | 14 | 15 | 2023-12-10 | 2023-12-17
MK-1084GMP-D | 0 | 4 | 2023-09-03 | 2023-10-01
MK-1084Dev-D | 4 | 12 | 2023-10-01 | 2023-11-26
MK-1084Setup-A1 | 0 | 1 | 2023-09-03 | 2023-09-10
MK-1084-A1 | 11 | 15 | 2023-11-19 | 2023-12-17
MK-1084-2-D | 14 | 15 | 2023-12-10 | 2023-12-17
EP-200-E | 5 | 8 | 2023-10-08 | 2023-10-29
Arrival-F | 0 | 1 | 2023-09-03 | 2023-09-10
Installation-F | 2 | 3 | 2023-09-17 | 2023-09-24
SAT-F | 7 | 9 | 2023-10-22 | 2023-11-05
Setup-G | 0 | 1 | 2023-09-03 | 2023-09-10
WaterTesting-G | 1 | 2 | 2023-09-10 | 2023-09-17
Cleaning-G | 2 | 3 | 2023-09-17 | 2023-09-24
Dev-G | 4 | 5 | 2023-10-01 | 2023-10-08
Reset-G | 5 | 6 | 2023-10-08 | 2023-10-15
GMP-G | 11 | 13 | 2023-11-19 | 2023-12-03
end-0 | 15 | 15 | 2023-12-17 | 2023-12-17

## optimized
| s | f | Start_Date | Finish_Date
start-0 | 0 | 0 | 2023-09-03 | 2023-09-03
MK-8591-C | 9 | 16 | 2023-11-05 | 2023-12-24
MK-1167-B | 12 | 16 | 2023-11-26 | 2023-12-24
MK-3543-1-B | 0 | 4 | 2023-09-03 | 2023-10-01
MK-3543-TroubleShooting-B | 4 | 5 | 2023-10-01 | 2023-10-08
MK-3543-2-B | 6 | 7 | 2023-10-15 | 2023-10-22
MK-3543-Requal-B | 7 | 8 | 2023-10-22 | 2023-10-29
MK-3543-3-B | 10 | 12 | 2023-11-12 | 2023-11-26
MK-3543-Cleaning-B | 16 | 18 | 2023-12-24 | 2024-01-07
MK-1084GMP-D | 0 | 4 | 2023-09-03 | 2023-10-01
MK-1084Dev-D | 4 | 12 | 2023-10-01 | 2023-11-26
MK-1084Setup-A1 | 12 | 13 | 2023-11-26 | 2023-12-03
MK-1084-A1 | 13 | 17 | 2023-12-03 | 2023-12-31
MK-1084-2-D | 17 | 18 | 2023-12-31 | 2024-01-07
EP-200-E | 0 | 3 | 2023-09-03 | 2023-09-24
Arrival-F | 0 | 1 | 2023-09-03 | 2023-09-10
Installation-F | 2 | 3 | 2023-09-17 | 2023-09-24
SAT-F | 6 | 8 | 2023-10-15 | 2023-10-29
Setup-G | 0 | 1 | 2023-09-03 | 2023-09-10
WaterTesting-G | 3 | 4 | 2023-09-24 | 2023-10-01
Cleaning-G | 6 | 7 | 2023-10-15 | 2023-10-22
Dev-G | 10 | 11 | 2023-11-12 | 2023-11-19
Reset-G | 11 | 12 | 2023-11-19 | 2023-11-26
GMP-G | 13 | 15 | 2023-12-03 | 2023-12-17
end-0 | 18 | 18 | 2024-01-07 | 2024-01-07

## draft1_list-v4
task-index | task-name | processing-time(weeks) | engineers | rooms | LM-40 - VBE 1 (BN##)* | LM-40 - VBE 2 (BN##) | LM-40 - Isolator (BN##) | PTM-300 (BN##)* | Sieve | Spray Dryer* | 50L Tank | Film Coater* | Autoinjector* (MRT) | 0-Patrick | 1-Mike | 2-Sergio | 3-Rob | 4-Syed | 5-Joe | 6-James T | 7-Liam | 8-Sadia | 9-Gabriella | 10-Jan
0 | start-0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | MK-8591-C | 7 | 2 | 1 | 1 | 1 | [8 empty] | 1 | [7 empty] | 1
2 | MK-1167-B | 4 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
3 | MK-3543-1-B | 4 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
4 | MK-3543-TroubleShooting-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
5 | MK-3543-2-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
6 | MK-3543-Requal-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
7 | MK-3543-3-B | 2 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
8 | MK-3543-Cleaning-B | 2 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
9 | MK-1084GMP-D | 4 | 2 | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1
10 | MK-1084Dev-D | 8 | 2 | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1
11 | MK-1084Setup-A1 | 1 | 2 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 | 1
12 | MK-1084-A1 | 4 | 2 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 | 1
13 | MK-1084-2-D | 1 | 2 | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1
14 | EP-200-E | 3 | 2 | 1 |  |  | 1
15 | Arrival-F | 1 | 2 | 1 | [8 empty] | 1 |  |  |  | 1 |  | 1
16 | Installation-F | 1 | 2 | 1 | [8 empty] | 1 |  |  |  | 1 |  | 1
17 | SAT-F | 2 | 2 | 1 | [8 empty] | 1 |  |  |  | 1 |  | 1
18 | Setup-G | 1 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
19 | WaterTesting-G | 1 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
20 | Cleaning-G | 1 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
21 | Dev-G | 1 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
22 | Reset-G | 1 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
23 | GMP-G | 2 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
24 | end-0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0