## Process_Dictionary
process | operation
A1 | Tablet Compression (XL100)
A2 | Tablet Compression (XM12)
B | Autoencapsulator
C | Manual Encapsulation
D | Spray Drying
E | Potent
F | Autoinjector
G | Bottle Filling/Liquid
H | Other
New equipment introduction
I | Non processing activities

## project_operations
Sept 3 2023- Feb 12 2024 |  |  | 24w
MK-8591 | C | C | C | C | C | C | C
MK-1167 | B | B | B | B
MK-3543 | B | B | B | B | A1 | A2
MK-1084 | D | D | D | D | D | A1 | A1 | A1 | A1 | H
EP-200 | C | C | C
MK-6552 | A1
MK-8507 | A1
MK-8527 | A1 | A2
MK-6916 | D | A1
MK-0616 | A1/H
MK-4646 | C
MK-3214 | C
MK-1708 | G | C
MK-7526 | C
MK-2828 | C
B-5020 | E
MK-2420 | E
MK-0472 | E

## draft1_list
process-index | process-name | processing-time(weeks) | engineers | rooms | LM-40 - VBE 1 (BN##)* | LM-40 - VBE 2 (BN##) | LM-40 - Isolator (BN##) | PTM-300 (BN##)* | Sieve | Spray Dryer* | Film Coater* | 0-Patrick | 1-Mike | 2-Sergio | 3-Rob | 4-Syed | 5-Joe | 6-James T | 7-Liam | 8-Sadia | 9-Gabriella | 10-Jan
0 | start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | MK-8591-C | 7 | 2 | 1 | 1 | 1 | [6 empty] | 1 | [7 empty] | 1
2 | MK-1167-B | 4 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 |  |  |  |  | 1
3 | MK-3543-1-B | 4 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 |  |  |  |  | 1
4 | MK-3543-2-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 |  |  |  |  | 1
5 | MK-3543-3-B | 2 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 |  |  |  |  | 1
6 | MK-1084GMP-D | 4 | 2 | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 1
7 | MK-1084Dev-D | 8 | 2 | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 1
8 | MK-1084Setup-A1 | 1 | 2 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1
9 | MK-1084-A1 | 4 | 2 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1
10 | MK-1084-2-D | 1 | 2 | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 1
11 | EP-200-C | 3 | 2 | 1 | 1 | 1 | [6 empty] | 1 | [7 empty] | 1
12 | end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## draft1_list-v5
process-index | process-name | processing-time(weeks) | engineers | rooms | LM-40 - VBE 1 (BN##)* | LM-40 - VBE 2 (BN##) | LM-40 - Isolator (BN##) | PTM-300 (BN##)* | Sieve | Spray Dryer* | 50L Tank | Film Coater* | Autoinjector* (MRT) | 0-Patrick | 1-Mike | 2-Sergio | 3-Rob | 4-Syed | 5-Joe | 6-James T | 7-Liam | 8-Sadia | 9-Gabriella | 10-Jan
0 | start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | MK-8591-C | 7 | 2 | 1 | 1 | 1 | [8 empty] | 1 | [7 empty] | 1
2 | MK-1167-B | 4 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
3 | MK-3543-1-B | 4 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
4 | MK-3543-TroubleShooting-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
5 | MK-3543-2-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
6 | MK-3543-Requal-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
7 | MK-3543-3-B | 2 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
8 | MK-3543-Cleaning-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
9 | MK-1084GMP-D | 4 | 2 | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1
10 | MK-1084Dev-D | 8 | 2 | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1
11 | MK-1084Setup-A1 | 1 | 2 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 | 1
12 | MK-1084-A1 | 4 | 2 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 | 1
13 | MK-1084-2-D | 1 | 2 | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1
14 | EP-200-C | 3 | 2 | 1 | 1 | 1 | [8 empty] | 1 | [7 empty] | 1
15 | Arrival-F | 1 | 2 | 1 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
16 | end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0

## draft1_list-v4
task-index | task-name | processing-time(weeks) | engineers | rooms | LM-40 - VBE 1 (BN##)* | LM-40 - VBE 2 (BN##) | LM-40 - Isolator (BN##) | PTM-300 (BN##)* | Sieve | Spray Dryer* | 50L Tank | Film Coater* | Autoinjector* (MRT) | 0-Patrick | 1-Mike | 2-Sergio | 3-Rob | 4-Syed | 5-Joe | 6-James T | 7-Liam | 8-Sadia | 9-Gabriella | 10-Jan
0 | start-0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | MK-8591-C | 7 | 2 | 1 | 1 | 1 | [8 empty] | 1 | [7 empty] | 1
2 | MK-1167-B | 4 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
3 | MK-3543-1-B | 4 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
4 | MK-3543-TroubleShooting-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
5 | MK-3543-2-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
6 | MK-3543-Requal-B | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
7 | MK-3543-3-B | 2 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
8 | MK-3543-Cleaning-B | 2 | 2 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
9 | MK-1084GMP-D | 4 | 2 | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1
10 | MK-1084Dev-D | 8 | 2 | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1
11 | MK-1084Setup-A1 | 1 | 2 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 | 1
12 | MK-1084-A1 | 4 | 2 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 | 1
13 | MK-1084-2-D | 1 | 2 | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1
14 | EP-200-C | 3 | 2 | 1 | 1 | 1 | [8 empty] | 1 | [7 empty] | 1
15 | Arrival-F | 1 | 2 | 1 | [8 empty] | 1 |  |  |  | 1 |  | 1
16 | Installation-F | 1 | 2 | 1 | [8 empty] | 1 |  |  |  | 1 |  | 1
17 | SAT-F | 2 | 2 | 1 | [8 empty] | 1 |  |  |  | 1 |  | 1
18 | Setup-G | 1 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
19 | WaterTesting-G | 1 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
20 | Cleaning-G | 1 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
21 | Dev-G | 1 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
22 | Reset-G | 1 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
23 | GMP-G | 2 | 2 | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  |  | 1
24 | end-0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0

## process_engineer_schedule
dates | Patrick | Mike | Sergio | Rob | Syed | Joe | James T | Liam | Sadia | Gabriella | Jan
2023-01-01
2023-01-08
2023-01-15
2023-01-22
2023-01-29
2023-02-05
2023-02-12
2023-02-19
2023-02-26
2023-03-05
2023-03-12
2023-03-19
2023-03-26
2023-04-02
2023-04-09
2023-04-16
2023-04-23
2023-04-30
2023-05-07
2023-05-14
2023-05-21
2023-05-28
2023-06-04
2023-06-11
2023-06-18
2023-06-25
2023-07-02
2023-07-09
2023-07-16
2023-07-23
2023-07-30
2023-08-06
2023-08-13
2023-08-20
2023-08-27
2023-09-03
2023-09-10
2023-09-17
2023-09-24
2023-10-01
2023-10-08
2023-10-15
2023-10-22
2023-10-29
2023-11-05
2023-11-12
2023-11-19
2023-11-26
2023-12-03
2023-12-10
2023-12-17
2023-12-24
2023-12-31
2024-01-08 | E | A |  | F
2024-01-15 | E | A |  | F |  | B
2024-01-22 | E | A/G | D | F | E | B
2024-01-29 | E | A/G | D | F | E | B
2024-02-05 | E | A/G | D | E,F | E | B
2024-02-12 | E | A/G | D | E,F | E | B
2024-02-19 | E | A/G | D | E,F | E, A
2024-02-26 | E |  | D | E,F | E, A
2024-03-04 | E |  | D | F | E, A
2024-03-11 | E |  | D | F | E, A
2024-03-18 | E |  | D | F | E, A
2024-03-25 |  |  | D | F | E, A
2024-04-01 | H |  | D | F | E, A
2024-04-08 | H |  | D | F
2024-04-15 | H |  | D | F
2024-04-22 | H | C | D | F
2024-04-29 |  | C/A |  | F
2024-05-06 |  | C/A |  | F |  |  | A
2024-05-13 |  | C/A |  | F |  |  | A
2024-05-20 |  | C | A1 | B |  |  | A/G
2024-05-27 |  | C |  | B |  |  | A/G
2024-06-03 |  | C |  | B |  |  | A/G | A2
2024-06-10 | E | C |  | B |  |  | A/G | A1
2024-06-17 | E | C |  | B |  |  | G | A1
2024-06-24 | E | C |  | B |  |  | G | A1
2024-07-01 | E | C | D | F |  |  | G | A1
2024-07-08 | E | G | D | F | [6 empty] | A2
2024-07-15 | E | G | D | F | [6 empty] | A2
2024-07-22 | E | G | D | F
2024-07-29 | B/A1 | G | D | F |  |  |  |  | I |  | H
2024-08-05 | B/A1 | G | D | F |  |  | A2 |  | I |  | H
2024-08-12 | B/A1 | G | D | F |  |  | A2 |  | I |  | H
2024-08-19 | B/A1 | G | D | F |  |  | A2 |  | I |  | H
2024-08-26 | B/A1 | G/I | D | F |  |  | A2 |  | I |  | H
2024-09-02 | B/A1 | G/I | D | F |  | E | A2/D |  | A1 | C | H
2024-09-09 | B/A1 | I | D | F |  | E | A2/D |  | A1 | C | H
2024-09-16 | B/A1 | I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-09-23 | B/A1 | I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-09-30 | B/A1 | C/I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-10-07 | B/A1 | C/I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-10-14 | B/A1 | C/I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-10-21 | B/A1 | C/I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-10-28 | B/A1 | C/I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-11-04 | B/A1 | I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-11-11 | B/A1 | A1/I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-11-18 | B/A1 | A1/I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-11-25 | B/A1 | A1/I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-12-02 | B/A1 | A1/I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-12-09 | B/A1 | A1/I | D | F/E |  | E | A2/D |  | A1 | C | H
2024-12-16
2024-12-23
2024-12-30
2025-01-06
2025-01-13
2025-01-20
2025-01-27
2025-02-03
2025-02-10
2025-02-17
2025-02-24
2025-03-03
2025-03-10
2025-03-17
2025-03-24
2025-03-31
2025-04-07
2025-04-14
2025-04-21
2025-04-28
2025-05-05
2025-05-12
2025-05-19
2025-05-26
2025-06-02
2025-06-09
2025-06-16
2025-06-23
2025-06-30
2025-07-07
2025-07-14
2025-07-21
2025-07-28
2025-08-04
2025-08-11
2025-08-18
2025-08-25
2025-09-01
2025-09-08
2025-09-15
2025-09-22
2025-09-29
2025-10-06
2025-10-13
2025-10-20
2025-10-27
2025-11-03
2025-11-10
2025-11-17
2025-11-24
2025-12-01
2025-12-08
2025-12-15
2025-12-22
2025-12-29
2026-01-05
2026-01-12
2026-01-19
2026-01-26

## draft1_resource_availability
engineers | rooms | LM-40 - VBE 1 (BN##)* | LM-40 - VBE 2 (BN##) | LM-40 - Isolator (BN##) | PTM-300 (BN##)* | Sieve | Spray Dryer* | Film Coater*
11 | 11 | 3 | 1 | 1 | 2 | 2 | 1 | 1

## process_equipment
process | operation | Blenders | LM-40 - VBE 1 (BN##)* | LM-40 - VBE 2 (BN##) | LM-40 - Isolator (BN##) | PTM-300 (BN##)* | Sieve | Comill | Hammermill | RC* | RC 2 | XL-100* | XM-12* | Film Coater* | Profill 1* | Profill 2 | Harro* | Icaps | Short ICAPS | Sade Weight Sorter | Sejong Weight Sorter 2 | Spray Dryer* | 50L Tank | 20, 100 L tanks | HME* | Isolators* | Autoinjector* (MRT) | TSG
A1 | Tablet Compression (XL100) |  | 1 |  |  | 1 | 1 |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 |  | 1
A2 | Tablet Compression (XM12) |  | 1 |  |  | 1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1
B | Autoencapsulator |  | 1 |  | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1
C | Manual Encapsulation |  | 1 | 1 | [10 empty] | 1 |  |  | 1 | 1 | 1 | 1 |  |  | 1
D | Spray Drying | [20 empty] | 1
E | Potent |  |  |  | 1 |  |  | 1 | [8 empty] | 1 | 1 |  | 1 | [5 empty] | 1
F | Autoinjector | [25 empty] | 1
G | Bottle Filling/Liquid | [21 empty] | 1
H | Other | [12 empty] | 1 | [10 empty] | 1 |  |  | 1
I | Non processing activities | [17 empty] | 1 | [5 empty] | 1

## equipment_schedule
dates | Blenders | LM-40 - VBE 1 (BN##)* | LM-40 - VBE 2 (BN##) | LM-40 - Isolator (BN##) | PTM-300 (BN##)* | Sieve | Comill | Hammermill | RC* | RC 2 | XL-100* | XM-12* | Film Coater* | Profill 1* | Profill 2 | Harro* | Icaps | Short ICAPS | Sade Weight Sorter | Sejong Weight Sorter 2 | Spray Dryer* | 50L Tank | 20, 100 L tanks | HME* | Isolators* | Autoinjector* (MRT) | TSG
2023-01-01
2023-01-08
2023-01-15
2023-01-22
2023-01-29
2023-02-05 |  | A | [13 empty] | A | A |  | A
2023-02-12 |  | A | [13 empty] | A | A |  | A
2023-02-19 |  | A | [13 empty] | A | A |  | A
2023-02-26 |  | A | [13 empty] | A | A |  | A
2023-03-05 |  | A | [13 empty] | A | A |  | A
2023-03-12
2023-03-19
2023-03-26
2023-04-02
2023-04-09 |  | A | [11 empty] | A |  |  | A |  | A
2023-04-16 |  | A | [11 empty] | A |  |  | A |  | A
2023-04-23 |  | A | [11 empty] | A |  |  | A |  | A
2023-04-30 |  | A |  |  | B | B |  |  | B |  | B |  |  | A |  |  | A |  | A
2023-05-07 |  |  |  |  | B | B |  |  | B |  | B
2023-05-14 |  |  |  |  | B | B |  |  | B |  | B
2023-05-21
2023-05-28
2023-06-04
2023-06-11 |  | A | [13 empty] | A
2023-06-18 |  | A | [13 empty] | A
2023-06-25 |  | A | [13 empty] | A
2023-07-02
2023-07-09
2023-07-16
2023-07-23
2023-07-30 |  | B | [11 empty] | B |  |  | B |  | B |  | A
2023-08-06 |  | B | [11 empty] | B |  |  | B |  | B |  | A
2023-08-13 |  | B | [11 empty] | B |  |  | B |  | B |  | A
2023-08-20 | [20 empty] | A
2023-08-27 | [20 empty] | A
2023-09-03 | [20 empty] | A
2023-09-10 | [20 empty] | A
2023-09-17 | [20 empty] | A
2023-09-24 | [20 empty] | A
2023-10-01 |  | B | [11 empty] | B |  |  | B |  | B |  | A
2023-10-08 |  | B | [11 empty] | B |  |  | B |  | B |  | A
2023-10-15 |  | B | [11 empty] | B |  |  | B |  | B |  | A
2023-10-22 |  | B | [11 empty] | B |  |  | B |  | B |  | A
2023-10-29 |  | B | [11 empty] | B |  |  | B |  | B |  | A
2023-11-05 |  | B | [11 empty] | B |  |  | B |  | B |  | A
2023-11-12 |  | B | [11 empty] | B |  |  | B |  | B |  | A
2023-11-19 | [20 empty] | A
2023-11-26 | [20 empty] | A
2023-12-03
2023-12-10
2023-12-17
2023-12-24
2023-12-31
2024-01-08
2024-01-15 | [21 empty] | G |  |  |  | F
2024-01-22 |  |  |  |  | A |  |  |  | A |  | A | [10 empty] | G |  |  |  | F
2024-01-29 |  |  |  | E | A |  |  |  | A |  | A | [5 empty] | B |  |  |  |  | G |  |  | E | F
2024-02-05 |  |  |  | E | A |  |  |  | A |  | A | [5 empty] | E |  |  |  |  | G |  |  | E | F
2024-02-12 |  |  |  | E | A |  |  |  | A |  | A | [5 empty] | E |  |  |  | D | G | D |  | E | F
2024-02-19 |  |  |  | E | A |  | E |  | A |  | A |  |  |  |  | MOVE TO 1261 | E |  | E |  | D | G | D |  | E | F
2024-02-26 |  | A |  | E |  |  | E |  | A |  | A | [7 empty] | E |  | D |  | D |  | E | F
2024-03-04 |  | A |  | E |  |  | E |  | A |  | A | MOVE IN XM12 | [6 empty] | E |  | D |  | D |  | E | F
2024-03-11 |  | A |  | E |  |  | E |  | A |  | A | HEPA | [6 empty] | E |  | D |  | D |  | E | F
2024-03-18 |  | A |  | E |  |  | E |  | A |  | A | [7 empty] | E |  | D |  | D |  | E | F
2024-03-25 |  | A |  | E |  |  | E |  | A |  | A | [7 empty] | E |  | D |  | D | HME audit trail automation | E | F
2024-04-01 |  | A |  | E |  |  | E |  | A |  | A | PM | [6 empty] | E |  | D |  | D |  | E | F
2024-04-08 |  |  |  | E | PM |  | E |  |  |  | PM | [7 empty] | E |  | D |  | D |  | E | F
2024-04-15 |  | A |  | E | A |  | E | [11 empty] | E |  | D |  | D |  | E
2024-04-22 |  | A |  | E | A |  | E |  |  |  | PM | [7 empty] | E |  | D |  | D |  | E
2024-04-29 |  | A | C | E | A |  | E |  | PM | [9 empty] | E |  | D |  | D |  | E | F
2024-05-06 |  | A | C | E | A |  | E |  | A |  | A | A2 |  | C |  |  | C |  | E |  | D |  | D |  | E | F
2024-05-13 |  | A | C | E | A |  | E |  | A |  | A | A2 |  | C |  |  | C |  | E |  | D |  | D |  | E | F
2024-05-20 |  |  | C | E | A |  | E |  | A |  | A | A2 |  | C |  |  | C |  | E |  | D |  | D
2024-05-27 |  |  | C | E | A |  | E |  | A |  | A | A2 |  | C |  |  | C |  | E |  | D |  | D |  | E
2024-06-03 |  | A2 | C | E | A |  | E |  | A |  | A | A2 |  | C |  |  | C |  | C |  | D |  | D |  | E
2024-06-10 |  | A2 | C | E | A |  | E |  | A |  | A | A2 |  | C |  |  | C |  | C | [5 empty] | E
2024-06-17 |  | A2 | C | E | A |  | E |  | A |  |  | A2 |  | C |  |  | C |  | C | [5 empty] | E
2024-06-24 |  | A2 | C | E | A |  | E |  | A |  |  | A2 |  | C |  |  | C |  | C | [5 empty] | E
2024-07-01 |  | A2 | C |  | A |  |  |  | A |  |  | A2 |  | C |  |  | C |  | C
2024-07-08
2024-07-15
2024-07-22
2024-07-29 |  |  |  | B | A2 | [6 empty] | A2 | H |  |  | B |  | I | B |  | D | G | D | I |  | F
2024-08-05 |  |  |  | B | A2 | [5 empty] | A1 | A2 | H |  |  | B |  | I | B |  | D | G | D | I |  | F
2024-08-12 |  |  |  | B | A2 | [6 empty] | A2 | H |  |  | B |  |  | B |  | D | G | D |  |  | F
2024-08-19 |  |  |  | B | [7 empty] | A2 | H |  |  | B |  |  | B |  | D |  | D |  |  | F
2024-08-26 |  |  |  | B | [6 empty] | A1 |  | H |  |  | B |  |  | B |  | D |  | D |  |  | F
2024-09-02 |  | A2 |  | B |  | A2 |  |  | A2 |  |  | A2 | H |  |  | B |  |  | B |  | D |  | D |  |  | F
2024-09-09 |  | A2 |  | B |  | A2 |  |  | A2 |  |  | A2 | H |  |  | B |  |  | B |  | D |  | D |  |  | F
2024-09-16 |  | A2 |  | B |  | A2 |  |  | A2 |  |  | A2 | H |  |  | B |  |  | B |  | D |  | D |  |  | F
2024-09-23 |  | A2 |  | B |  | A2 |  |  | A2 |  |  | A2 | H |  |  | B |  |  | B |  | D |  | D |  |  | F
2024-09-30 |  | A/C |  | B | A1 | A2 |  |  | A2 |  | A1 | A2 | H |  |  | B |  |  | B | C | D |  | D
2024-10-07 |  | C |  | B | A1 | A1 |  |  | A2 |  | A1 | A2 | H |  |  | B |  |  | B | C | D |  | D
2024-10-14 |  | C |  | B | A1 | A1 |  |  |  |  | A1 |  |  |  |  | B |  |  | B | C | D |  | D
2024-10-21 |  | C |  | B | A1 | A1 |  |  |  |  | A1 |  |  |  |  | B |  |  | B | C | D |  | D | H
2024-10-28 |  | C |  | B | A1 | A1 |  |  |  |  | A1 |  |  | C |  | B |  | C | C |  | D |  | D | H | E
2024-11-04 |  | A1 |  | B | A |  |  |  | A1 |  | A1 |  |  | C |  | B |  | C | C |  | D |  | D | H | E | F
2024-11-11 |  | A1 |  | B |  |  |  |  | A1 |  | A1 |  |  | C |  | B | E | C | C | B | D |  | D | H | E | F
2024-11-18 |  | A1 |  | B |  |  |  |  | A1 |  | A1 |  |  | C |  | B | E | C | C | B | D |  | D | H | E | F
2024-11-25 |  | A1 |  | B |  |  |  |  | A1 |  | A1 |  |  | C |  | B | E | C | C | B | D |  | D | H | E | F
2024-12-02 |  | A1 |  | B |  |  |  |  | A1 |  | A1 |  |  | C |  | B | E | C |  | B | D |  | D | H | E | F
2024-12-09 |  | A1 |  | B |  |  |  |  | A1 |  | A1 |  |  |  |  | B | E | C |  | B | D |  | D |  | E | F
2024-12-16 |  | A1 |  | B |  |  |  |  | A1 |  | A1 |  |  |  |  | B | E | C |  | B | D |  | D |  | E | F
2024-12-23 |  | A1 | [6 empty] | A1 |  | A1 |  |  |  |  | B | E | C |  |  | D |  | D |  | E | F
2024-12-30 |  | A1 | [6 empty] | A1 |  | A1 |  |  |  |  | B | E | C |  |  | D |  | D |  | E | F
2025-01-06 |  | A1 | [6 empty] | A1 |  | A1 |  | A1 |  |  | B | E | C |  |  | D |  | D |  | E | F
2025-01-13 |  | A1 | [6 empty] | A1 |  | A1 |  | A1 |  |  | B | E | C |  |  | D |  | D |  | E | F
2025-01-20 |  | A1 | [6 empty] | A1 |  | A1 |  | A1 |  |  | B |  | C |  |  | D |  | D |  | E
2025-01-27 |  | A1 | [6 empty] | A1 |  | A1 |  | A1 |  |  | B |  | C |  |  | D |  | D |  | E |  | H
2025-02-03 |  | A1 | [6 empty] | A1 |  | A1 |  | A1 |  |  | B |  | C |  | B | D |  | D |  | E |  | H
2025-02-10 |  | A1 | [6 empty] | A1 |  | A1 |  | A1 |  |  | B |  | C |  | B | D |  | D |  | E |  | H
2025-02-17 |  | A1 | [6 empty] | A1 |  | A1 |  | A1 |  |  | B | E | C |  | B | D |  | D |  | E |  | H
2025-02-24 |  | A1 | [6 empty] | A1 |  | A1 |  | A1 |  |  | B | E | C |  | B | D |  | D |  | E |  | H
2025-03-03 |  | A1 | [6 empty] | A1 |  | A1 |  |  |  |  | B | E | C |  | B | D |  |  |  | E |  | H
2025-03-10 |  | A1 | [6 empty] | A1 |  | A1 |  |  |  |  | B | E | C |  | B | D |  |  |  | E |  | H
2025-03-17 |  | A1 | [6 empty] | A1 |  | A1 |  |  |  |  | B | E | C |  | B | D |  |  |  | E |  | H
2025-03-24 |  | A1 | [6 empty] | A1 |  | A1 |  |  |  |  | B | E | C |  | B |  |  |  |  | E |  | H
2025-03-31 |  | A1 | [6 empty] | A1 |  | A1 |  |  |  |  | B | E | C |  | B | [6 empty] | H
2025-04-07 |  | A1 | [6 empty] | A1 |  | A1 |  |  |  |  | B | E | C |  | B
2025-04-14 | [15 empty] | B | E | C |  | B
2025-04-21 | [15 empty] | B | E | C |  | B
2025-04-28 | [15 empty] | B | E | C |  | B
2025-05-05 | [15 empty] | E | E | C
2025-05-12 | [15 empty] | E | E | C
2025-05-19 | [15 empty] | E | E | C
2025-05-26 | [15 empty] | E | E | C
2025-06-02 | [15 empty] | E | E | C
2025-06-09 | [15 empty] | E | E | C
2025-06-16 | [15 empty] | E | E
2025-06-23 | [15 empty] | E | E
2025-06-30 | [15 empty] | E | E
2025-07-07
2025-07-14
2025-07-21
2025-07-28
2025-08-04
2025-08-11
2025-08-18
2025-08-25
2025-09-01
2025-09-08
2025-09-15
2025-09-22
2025-09-29
2025-10-06
2025-10-13
2025-10-20
2025-10-27
2025-11-03
2025-11-10
2025-11-17
2025-11-24
2025-12-01
2025-12-08
2025-12-15
2025-12-22
2025-12-29
2026-01-05
2026-01-12
2026-01-19
2026-01-26

## rooms_schedule
dates | 1211 | 1212 | 1213 | 1214 | 1215 | 1233 | 1241 | 1242 | 1261 | 1262 | 1263
2023-01-01
2023-01-08
2023-01-15
2023-01-22
2023-01-29
2023-02-05
2023-02-12
2023-02-19
2023-02-26
2023-03-05
2023-03-12
2023-03-19
2023-03-26
2023-04-02
2023-04-09
2023-04-16
2023-04-23
2023-04-30
2023-05-07
2023-05-14
2023-05-21
2023-05-28
2023-06-04
2023-06-11
2023-06-18
2023-06-25
2023-07-02
2023-07-09
2023-07-16
2023-07-23
2023-07-30
2023-08-06
2023-08-13
2023-08-20
2023-08-27
2023-09-03
2023-09-10
2023-09-17
2023-09-24
2023-10-01
2023-10-08
2023-10-15
2023-10-22
2023-10-29
2023-11-05
2023-11-12
2023-11-19
2023-11-26
2023-12-03
2023-12-10
2023-12-17
2023-12-24
2023-12-31
2024-01-08 |  | B
2024-01-15 | A | B | G | A |  |  | A | F |  |  | B
2024-01-22 | A | B | G | A |  |  | A | F
2024-01-29 | A | B | G | A |  |  | A | F | E |  | B
2024-02-05 | A | B | G | A |  |  | A | F | E |  | B
2024-02-12 | A | B | G | A | D |  | A | F | E |  | B
2024-02-19 | A |  | G | A | D |  |  | F | E
2024-02-26 | A |  |  | A | D |  |  | F | E |  | E
2024-03-04 | A |  |  | A | D |  | 1167 closeout | F | E |  | E
2024-03-11 | A | A2 |  | A | D |  | PM - DFB | F | E |  | E
2024-03-18 | A | A2 |  | A | D |  |  | F | E |  | E
2024-03-25 | A | A2 |  | A | D |  |  | F | E
2024-04-01 |  | A2 |  |  | D |  |  | F | E
2024-04-08 |  | A2 |  |  | D |  |  | F | E | H
2024-04-15 |  | A2 |  |  | D |  |  | F | E | H
2024-04-22 | A | A2 |  |  | D |  |  | F | E | H
2024-04-29 | A | A2 |  | A |  |  |  | F | E | H | C
2024-05-06 | A | A2 |  | A |  |  |  | F | E | H | C
2024-05-13 | A | A2 |  | A |  | A |  | F | E | H | C
2024-05-20 | A | A2 |  | A |  | B |  |  | E | H | C
2024-05-27 | A |  |  | A |  | A |  |  | E |  | C
2024-06-03 | A |  |  | A2 |  |  |  |  | E |  | C
2024-06-10 | A |  |  | A2 |  |  |  |  | E |  | C
2024-06-17 |  |  |  | A2 |  | A2 |  |  | E |  | C
2024-06-24 |  |  |  | A2 |  | C |  | F |  |  | C
2024-07-01 |  |  |  | A2 |  | A2 |  | F |  |  | C
2024-07-08
2024-07-15
2024-07-22
2024-07-29 |  | A2 | H |  | D |  | I | F | B | I | I
2024-08-05 | A1 | A2 | H |  | D |  |  | F | B | I
2024-08-12 |  | A2 | H |  | D | A2 |  | F | B | I
2024-08-19 |  |  | H |  | D |  |  | F | B | I
2024-08-26 | A1 |  | H |  | D |  |  | F | B | I
2024-09-02 |  | A2 | H | A2 | D | H | A2 | F | B | I
2024-09-09 |  | A2 | H | A2 | D | A2 | A2 | F | B | I
2024-09-16 |  | A2 | H | A2 | D | D | A2 | F | B | I
2024-09-23 |  | A2 | H | A2 | D | A2 | A1 | F | B | I
2024-09-30 | A1 | A2 | H | A2/A1 | D | D | A1 | I | B
2024-10-07 | A1 | A2 | H | A1 | D | A2 |  | I | B |  | C
2024-10-14 | A1 |  | H | A1 | D |  |  | I | B |  | C
2024-10-21 | A1 |  |  | A1 | D | A1 |  | I | B | H | C
2024-10-28 | A1 |  |  | A1 | D | B | C | I | B | H | C
2024-11-04 |  |  |  |  | D | C | C | I | B | H | C
2024-11-11 | A1 | B |  | A1 | D |  | C | I | E | H | C
2024-11-18 | A1 | B |  | A1 | D | D | C |  | E | H | C
2024-11-25 | A1 | B |  | A1 | D | C | C | F | E | H | C
2024-12-02 | A1 | B |  | A1 | D |  | C | F | E |  | C
2024-12-09 | A1 | B |  | A1 | D | A1 | C | F | E |  | C
2024-12-16 | A1 | B |  | A1 | D | D | C | F | E |  | C
2024-12-23
2024-12-30
2025-01-06 | A1 | B | A1 | A1 | D | D |  | F | E |  | C
2025-01-13 | A1 | B | A1 | A1 | D |  |  | F | E |  | C
2025-01-20 | A1 | B | A1 | A1 | D |  |  | I | E |  | C
2025-01-27 | A1 | B | A1 | A1 | D | C |  | I | E |  | C
2025-02-03 | A1 | B | A1 | A1 | D |  |  | I | E |  | C
2025-02-10 | A1 | B | A1 | A1 | D | D |  | I | E |  | C
2025-02-17 | A1 | B | A1 | A1 | D | A1 |  | I | E |  | C
2025-02-24 | A1 | B | A1 | A1 | D | A1/B |  | I |  |  | C
2025-03-03 | A1 | B |  | A1 | D | B |  |  |  |  | C
2025-03-10 | A1 | B |  | A1 | D | C |  |  |  |  | C
2025-03-17 | A1 | B |  | A1 | D | D
2025-03-24 | A1 | B |  | A1 |  | A1
2025-03-31 | A1 | B |  | A1 |  | A1
2025-04-07 | A1 | B |  | A1
2025-04-14 |  | B
2025-04-21 |  | B
2025-04-28 |  | B
2025-05-05
2025-05-12
2025-05-19
2025-05-26
2025-06-02
2025-06-09
2025-06-16
2025-06-23
2025-06-30
2025-07-07
2025-07-14
2025-07-21
2025-07-28
2025-08-04
2025-08-11
2025-08-18
2025-08-25
2025-09-01
2025-09-08
2025-09-15
2025-09-22
2025-09-29
2025-10-06
2025-10-13
2025-10-20
2025-10-27
2025-11-03
2025-11-10
2025-11-17
2025-11-24
2025-12-01
2025-12-08
2025-12-15
2025-12-22
2025-12-29
2026-01-05
2026-01-12
2026-01-19
2026-01-26

## vbes_schedule
dates | 1 | 2 | 3 | LM40 Blender VBE #4 | 5 | Manual Encap 1 of 2 #6 | Manual Encap 2 of 2 # 7 | 8 | Solvent 9 | 10 | Large, well vert space 11 | Large, cont liner, vert space 12 | LM40 Blender 13, OOS | Small IPC 16
2023-01-01
2023-01-08
2023-01-15
2023-01-22
2023-01-29
2023-02-05
2023-02-12
2023-02-19
2023-02-26
2023-03-05
2023-03-12
2023-03-19
2023-03-26
2023-04-02
2023-04-09
2023-04-16
2023-04-23
2023-04-30
2023-05-07
2023-05-14
2023-05-21
2023-05-28
2023-06-04
2023-06-11
2023-06-18
2023-06-25
2023-07-02
2023-07-09
2023-07-16
2023-07-23
2023-07-30
2023-08-06
2023-08-13
2023-08-20
2023-08-27
2023-09-03
2023-09-10
2023-09-17
2023-09-24
2023-10-01
2023-10-08
2023-10-15
2023-10-22
2023-10-29
2023-11-05
2023-11-12
2023-11-19
2023-11-26
2023-12-03
2023-12-10
2023-12-17
2023-12-24
2023-12-31
2024-01-08
2024-01-15
2024-01-22
2024-01-29
2024-02-05
2024-02-12
2024-02-19
2024-02-26 |  |  |  | 1214 |  | 1263 | 1263 |  | 1261 |  | OOS/1251 | 1213 | 1263 | 1211
2024-03-04
2024-03-11
2024-03-18
2024-03-25
2024-04-01
2024-04-08
2024-04-15 |  |  |  | 1214 |  | 1263 | 1263 |  | 1261 |  | OOS/1251 | 1213 | 1262 | 1211
2024-04-22
2024-04-29 |  |  |  | 1263 | [8 empty] | 1251
2024-05-06
2024-05-13
2024-05-20
2024-05-27
2024-06-03
2024-06-10
2024-06-17
2024-06-24
2024-07-01
2024-07-08
2024-07-15
2024-07-22
2024-07-29
2024-08-05
2024-08-12
2024-08-19
2024-08-26
2024-09-02
2024-09-09
2024-09-16
2024-09-23
2024-09-30
2024-10-07
2024-10-14
2024-10-21
2024-10-28
2024-11-04
2024-11-11
2024-11-18
2024-11-25
2024-12-02
2024-12-09
2024-12-16
2024-12-23
2024-12-30
2025-01-06
2025-01-13
2025-01-20
2025-01-27
2025-02-03
2025-02-10
2025-02-17
2025-02-24
2025-03-03
2025-03-10
2025-03-17
2025-03-24
2025-03-31
2025-04-07
2025-04-14
2025-04-21
2025-04-28
2025-05-05
2025-05-12
2025-05-19
2025-05-26
2025-06-02
2025-06-09
2025-06-16
2025-06-23
2025-06-30
2025-07-07
2025-07-14
2025-07-21
2025-07-28
2025-08-04
2025-08-11
2025-08-18
2025-08-25
2025-09-01
2025-09-08
2025-09-15
2025-09-22
2025-09-29
2025-10-06
2025-10-13
2025-10-20
2025-10-27
2025-11-03
2025-11-10
2025-11-17
2025-11-24
2025-12-01
2025-12-08
2025-12-15
2025-12-22
2025-12-29
2026-01-05
2026-01-12
2026-01-19
2026-01-26